## EXAMPLE Schedule of Reporting
Title: | Children's Futures BCAP
Organization Name: | Health Plan of NJ
Contact Name: | Susan Smith
Contact Phone Number: | 609-528-8400
Submission Date: | 2006-06-15
Date Report Due | Project Measurement Form, PDSA Cycles by BCAP Category | Pilot Data Report* | Team Assessment | Sustainability and Diffusion Scales | Common Measures
2006-04-15 | Baseline | Baseline | Baseline
2006-06-15 | X | X | X
2006-08-15 | X | X | X | Baseline | Baseline
2006-10-15 | X | X | X | X | X
2006-12-15 | X | X | X | X | X
2007-03-15 |  |  |  |  | X
2007-06-15 |  |  |  |  | X
2007-09-15 |  |  |  |  | X
2007-12-15 |  |  |  |  | X
2008-03-15 |  |  |  |  | X
2008-06-15 |  |  |  |  | X
2008-09-15 |  |  |  |  | X
2008-12-15 |  |  |  |  | X
* - The Pilot Data Report allows space for monthly data collection by MCO.
PRINTING INSTRUCTIONS: All pages are oriented as 'portrait' for printing, with the exception of the Pilot Measure Graphs which are oriented 'landscape.'
EXAMPLE
BCAP Quality
Workbook

## EXAMPLE Pilot Planning Tool
Title: | Children's Futures BCAP |  |  | Submission Date: | 2006-06-14
Organization Name: | Health Plan of NJ |  |  | CHCS Approval Date:
Contact Name: | Susan Smith |  | Review Dates | 2006-04-20
Contact Phone Number: | 609-528-8400
Submission Date: | 2006-06-15
Overall Project Aim | To encourage 75% more providers to perform standardized developmental screening (SDS) in children, age 6-36 months, during preventive visits.
Typology Category | Identification | Stratification | Outreach | Intervention
Typology Aim (Please state quantitatively.) | Identify 100% of preventive visits by PCPs for members age 6-36months for which a standardized developmental screening was performed and to identify the PCPs who perform preventive visits for these members. | Stratify 100% of PCPs by number of preventive visits with SDS to determine "high-leverage" PCPs (those provider with both high volume of preventive visit and high opportunity for improvement). Definitions: "hi-vol"=PCPs >100prev visits; "hi-opportunity"=PCPs w/ <50% of preventive visits with SDS; "hi-leverage"=PCPs who are both hi-vol and hi-opportunity | Conduct provider education in-services at 100% of the high-leverage provider sites. | Ensure that 100% of hi-leverage PCPs perform SDS as part of preventive visit at least 50% of the time.
Measure(s) for test of change: | Percent of preventive visits for members age 6-36 months assessed with SDS. | % Hi-Volume PCPs | % of Hi-Leverage providers receiving educational in-service | SDS screening Rate for Hi-Leverage providers
Numerator | # of preventive visit for members age 6-36 month with SDS | PCPs with >100 preventive visits per year | # of Hi-Leverage providers receiving educational in-service | # of hi-leverage PCPs with 50% or higher rate for SDS
Denominator | # of preventive visits for members age 6-36 months | # of PCPs performing preventive visits in members age 6-36 months | # of hi-leverage providers | # of hi-leverage PCPs
Measure(s) for test of change: | % of PCPs performing preventive visits in members age 6-36 months | % Hi-Opportunity PCPs | n/a | n/a
Numerator | # of PCPs performing preventive visits in members age 6-36 months | PCPs with fewer than 50% of preventive visits with SDS | n/a | n/a
Denominator | ALL providers serving the population of children, age 6-36 months. | # of PCPs performing preventive visits in members age 6-36 months | n/a | n/a
Measure(s) for test of change: |  | % Hi-Leverage PCPs | n/a | n/a
Numerator |  | # of PCPs that are both Hi-Volume and Hi-Opportunity | n/a | n/a
Denominator |  | # of PCPs performing preventive visits in members age 6-36 months | n/a | n/a
Description of the first change activity you will try: | PDSA 1: | PDSA 1: | PDSA 1: | PDSA 1:
PLAN | decided on specifications for members with asthma using claims data. | Plan strategy to make highest impact with outreach efforts. | Research SDS tools and develop evidence-based presentation for Hi-Leverage PCPs and office staff. | Remind providers of FFS reimbursement for SDS (CPT code 96110). Simplify documentation and paperwork for reimbursement.
DO | ran program code and calculated asthma prevalence. | initially selected two practices (total of 6 sites) with greatest number of patients and greatest willingness and readiness to participate. | Selected practices were very excited to participate in the pilot and were invited to participate on the BCAP team. | Provided staff with local and practice data on asthma prevalence, effective strategies for improving member adherence to prescribed treatment, member-specific utilization histories
STUDY | compared SDS assessment rates with published rates and experience of other NJ plans - they were similar. | redefined specs several times as we learned more about experience of other BCAP projects; experience was useful in focusing our efforts on highest risk members. | Inviting practices to participate in planning was useful in gaining their commitment to the pilot outcomes. | Determined that audience was too large making it difficult to engage members.
ACT | to explore other methods for identifying providers performing SDS. | no planned modifications unless feedback from providers and members suggest the need. | Consider using experience team members from practice sites to help bring up new sites. | Next event will be more focused and include only providers and their direct clinical support staff.
What is the target date for starting this change activity? | 2006-06-15 | 2006-06-15 | 2006-06-15 | 2006-08-02
What barriers do you anticipate and what strategies will you use to address them? | Medical claims lag - develop alternative ways for more timely identification of members with asthma (PCPs, clinic site,E Rs, hospital for admissions, customer services, pharmacy claims) | Deciding among various approached to identifying high risk members for intervention - plan to review literature for criteria that correlate with subsequent ER and IP utilization. Barrier addressed satisfactorily. | For providers - Competition for provider and clinic staff time - plan campaign that will be attention getting and meaningful to providers/staff, and plan to offer lunch for staff as an incentive/reward. For members - ability to contact member by phone - plan to contact provider offices to identify most current phone number; mail letter to member to call FHP-NJ. | Ability to engage providers - plan to make reports very easy to read and very actionable clinically. Reluctance/discomfort of staff with teaching asthma management to members - plan for participative training.
What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this pilot activity? | IT services; FHP-NJ committees; other delivery systems; clinic sites; hospitals; E Rs | Methodist FHP-NJ Physician Advisory Group; IT services; FHP-NJ committees; other delivery systems; office practices | IT services; clinic site directors, providers and staff, members | Asthma Alliance,IT services; clinic site directors, providers and staff, members
What Technical Assistance (TA) do you need to be able to move forward? | Feedback on approach and technical input. | Feedback on approach and technical input. | Feedback on approach and technical input. | Workshop demos of academic detailing
Have any issues arisen with enrollment into or engagement of patients in the intervention? | No | NO | Yes, some providers are withholding participation due to claims disputes. | Yes, some providers are withholding participation due to claims disputes.
Have any details of the intervention strategy changed since the last reporting period? | No | Yes, working with IT liaison to prioritize requests.
Overall Aim Measure #1 | % of high-leverage providers performing SDS
Description of measure | Rate of providers serving the target population who administer the standardized developmental screening (SDS) in children, age 6-36 months, during preventive visits.
Population | Providers serving the population of children, age 6-36 months.
Numerator | Providers serving the population of children, age 6-36 months administering the SDS in children.
Denominator | Targeted providers serving the population of children, age 6-36 months.
Overall Aim Measure #2 | % of ALL providers performing SDS
Description of measure | Rate of providers serving the target population who administer the standardized developmental screening (SDS) in children, age 6-36 months, during preventive visits.
Population | Providers serving the population of children, age 6-36 months.
Numerator | Providers serving the population of children, age 6-36 months administering the SDS in children.
Denominator | ALL providers serving the population of children, age 6-36 months.
Overall Aim Measure #3 | Enter the name of the measure on the Pilot Planning Tool Tab
Description of measure | Enter this descriptive information on the Pilot Planning Tool Tab
Population | Enter this descriptive information on the Pilot Planning Tool Tab
Numerator | Enter this descriptive information on the Pilot Planning Tool Tab
Denominator | Enter this descriptive information on the Pilot Planning Tool Tab
Overall Aim Measure #4 | Enter the name of the measure on the Pilot Planning Tool Tab
Description of measure | Enter this descriptive information on the Pilot Planning Tool Tab
Population | Enter this descriptive information on the Pilot Planning Tool Tab
Numerator | Enter this descriptive information on the Pilot Planning Tool Tab
Denominator | Enter this descriptive information on the Pilot Planning Tool Tab
Note on B12: Begin with the end in mind. Are these pilot measures aligned to the desired outcome? If, not you might need to select other pilot measures that will lead to the final results.
Note on C12: Begin with the end in mind. Are these pilot measures aligned to the desired outcome? If, not you might need to select other pilot measures that will lead to the final results.
Note on D12: Begin with the end in mind. Are these pilot measures aligned to the desired outcome? If, not you might need to select other pilot measures that will lead to the final results.
Note on E12: Begin with the end in mind. Are these pilot measures aligned to the desired outcome? If, not you might need to select other pilot measures that will lead to the final results.
EXAMPLE
BCAP Quality
Workbook
EXAMPLE
BCAP Quality
Workbook

## EXAMPLE PDSA Cycles
Plan, Do, Study, Act
Title: | Children's Futures BCAP
Organization Name: | Health Plan of NJ
Contact Name: | Susan Smith
Contact Phone Number: | 609-528-8400
Submission Date: | 2006-06-15
The following questions should guide your thinking around changes/ improvements in your intervention. As you test these changes, please document your activities in the PDSA section below. The Test of Change reporting is structured to reinforce the use of Plan - Do - Study - Act iterative cycles (PDSA). Describe the change activities you plan on implementing or have already implemented. You may have multiple small tests of change to reach your aim by typology, as well as your overall project aim.
Be sure to consider these questions as you document your PDSA cycles: | What barriers do you anticipate and what strategies will you use to address them? | What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? | What Technical Assistance (TA) do you need to be able to move forward? | Have any issues arisen with enrollment into or engagement of patients in the intervention? | Have any details of the intervention strategy changed since the last reporting period?
Identification: PDSA Cycle #1 (Please enter information in the appropriate cells on the Pilot Planning Tool tab)
Date: | 2006-06-15
Plan: | decided on specifications for members with asthma using claims data.
Do: | ran program code and calculated asthma prevalence.
Study: | compared SDS assessment rates with published rates and experience of other NJ plans - they were similar.
Act: | to explore other methods for identifying providers performing SDS.
Identification: PDSA Cycle #2 (Please enter information in the appropriate cells below)
Date:
Plan:
Do:
Study:
Act:
Identification: PDSA Cycle #3 (Please enter information in the appropriate cells below)
Date:
Plan:
Do:
Study:
Act:
Stratification: PDSA Cycle #1 (Please enter information in the appropriate cells on the Pilot Planning Tool tab)
Date: | 2006-06-15
Plan: | Plan strategy to make highest impact with outreach efforts.
Do: | initially selected two practices (total of 6 sites) with greatest number of patients and greatest willingness and readiness to participate.
Study: | redefined specs several times as we learned more about experience of other BCAP projects; experience was useful in focusing our efforts on highest risk members.
Act: | no planned modifications unless feedback from providers and members suggest the need.
Stratification: PDSA Cycle #2 (Please enter information in the appropriate cells below)
Date:
Plan:
Do:
Study:
Act:
Stratification: PDSA Cycle #3 (Please enter information in the appropriate cells below)
Date:
Plan:
Do:
Study:
Act:
Outreach: PDSA Cycle #1 (Please enter information in the appropriate cells on the Pilot Planning Tool tab)
Date: | 2006-06-15
Plan: | Research SDS tools and develop evidence-based presentation for Hi-Leverage PCPs and office staff.
Do: | Selected practices were very excited to participate in the pilot and were invited to participate on the BCAP team.
Study: | Inviting practices to participate in planning was useful in gaining their commitment to the pilot outcomes.
Act: | Consider using experience team members from practice sites to help bring up new sites.
Outreach: PDSA Cycle #2 (Please enter information in the appropriate cells below)
Date: | 2006-07-15
Plan: | Providers identified as high leverage for the first round of practice sites were assigned to detailing team co-led by QI and provider relations staff.
Do: | The first few sessions to providers were reviewed with the Chief Medical Director to review the process.
Study: | Several sessions were completed and each of those practices were detailed in use of the SDS assessment.
Act: | Use review of first few sessions to refine the process.
Outreach: PDSA Cycle #3 (Please enter information in the appropriate cells below)
Date: | 2006-10-15
Plan: | Arrange for CMO or Medical Director to make outreach calls in an effort to reach practices who have not scheduled academic detailing sessions.
Do: | Schedule adjustments were made and a computer was set up so calls could be made from asthma disease manager's home until 7 PM.
Study: | Aside from computer set up, there were no barriers encountered.
Act: | Process to involve CMO or Medical Director are now routine when initial attempts to arrange academic detailing sessions on the SDS assessment are not successful after 1 week of attempts by QI staff and success will be communicated to other departments engaged in outreach efforts to network providers.
Intervention: PDSA Cycle #1 (Please enter information in the appropriate cells on the Pilot Planning Tool tab)
Date: | 2006-08-02
Plan: | Remind providers of FFS reimbursement for SDS (CPT code 96110). Simplify documentation and paperwork for reimbursement.
Do: | Provided staff with local and practice data on asthma prevalence, effective strategies for improving member adherence to prescribed treatment, member-specific utilization histories
Study: | Determined that audience was too large making it difficult to engage members.
Act: | Next event will be more focused and include only providers and their direct clinical support staff.
Intervention: PDSA Cycle #2 (Please enter information in the appropriate cells below)
Date: | 2006-09-22
Plan: | Conducted second academic detailing vists using feedback from initial visit to modify process.
Do: | Provided same presentation as for first event with two changes: only providers and their direct clinical support staff were included and specific members of the participating providers were chosen to review as part of the presentation.
Study: | More strategically targeted audience was much better engaged and appreciative of the information.
Act: | Continue with modified presentation format and evaluate provider and staff response.
Intervention: PDSA Cycle #3 (Please enter information in the appropriate cells below)
Date:
Plan:
Do:
Study:
Act:
Note on A12: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A13: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A14: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A15: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A18: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A19: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A20: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A21: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A24: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A25: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A26: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A27: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A30: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A31: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A32: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A33: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A36: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A37: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A38: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A39: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A42: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A43: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A44: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A45: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A48: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A49: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A50: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A51: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A54: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A55: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A56: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A57: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A60: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A61: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A62: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A63: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A66: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A67: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A68: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A69: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A72: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A73: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A74: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A75: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A78: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A79: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A80: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A81: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
P D
A S
EXAMPLE
BCAP Quality
Workbook

## EXAMPLE Pilot Data Report
|  |  |  | PILOT MEASURES |  | Yes
No
Title: |  | Children's Futures BCAP
Organization Name: |  | Health Plan of NJ
Contact Name: |  | Susan Smith
Contact Phone Number: |  | 609-528-8400
Submission Date: |  | 2006-06-15
Identification measure #1 | Percent of preventive visits for members age 6-36 months assessed with SDS.
Description of measure | Claims data using CPT codes to identify preventive visits for members age 6 to 36 months. Age based on end of reporting time period. CPT codes are: 99290,99291, 99292,99293, 99295.
Population | All members age 6-36 months.
Numerator | # of preventive visit for members age 6-36 month with SDS
Denominator | # of preventive visits for members age 6-36 months
Are the data in the numerator cumlative over time (yes/no)? |  |  | Yes | Are the data in the denominator cumlative over time (yes/no)? | Yes
Data Source |  |  | Medical claims data from the EPIPHYS claims system.
Notes regarding the data for this measure: |  |  | 3 month lag for 99% completeness of submitted claims from providers.
Pilot population
Report Date | Numerator (number) | Denominator (number) | Rate or results
2006-04-15 | 2000 | 26828 | 7.455%
2006-06-15 | 2059 | 27574 | 7.467%
2006-08-15 | 2059 | 27574 | 7.467%
2006-10-15 | 964 | 12528 | 7.695%
2006-12-15 |  |  | #DIV/0!
2007-03-15 |  |  | #DIV/0!
2007-06-15 |  |  | #DIV/0!
2007-09-15 |  |  | #DIV/0!
2007-12-15 |  |  | #DIV/0!
2008-03-15 |  |  | #DIV/0!
2008-06-15 |  |  | #DIV/0!
2008-09-15 |  |  | #DIV/0!
2008-12-15 |  |  | #DIV/0!
Identification measure #2 | % of PCPs performing preventive visits in members age 6-36 months
Description of measure | Filtered by provider ID#. Claims data using CPT codes to identify preventive visits for members age 6 to 36 months. Age based on end of reporting time period. CPT codes are: 99290,99291, 99292,99293, 99295.
Population | All PCPs for members age 6-36 months.
Numerator | # of PCPs performing preventive visits in members age 6-36 months
Denominator | ALL providers serving the population of children, age 6-36 months.
Are the data in the numerator cumlative over time (yes/no)? |  |  | Yes | Are the data in the denominator cumlative over time (yes/no)? | Yes
Data Source |  |  | Medical claims data from the EPIPHYS claims system.
Notes regarding the data for this measure: |  |  | 3 month lag for 99% completeness of submitted claims from providers.
Pilot population
Report Date | Numerator (number) | Denominator (number) | Rate or results
2006-04-15 | 50 | 453 | 11.04%
2006-06-15 | 52 | 404 | 12.87%
2006-08-15 | 64 | 458 | 13.97%
2006-10-15 | 63 | 459 | 13.73%
2006-12-15 |  |  | #DIV/0!
2007-03-15 |  |  | #DIV/0!
2007-06-15 |  |  | #DIV/0!
2007-09-15 |  |  | #DIV/0!
2007-12-15 |  |  | #DIV/0!
2008-03-15 |  |  | #DIV/0!
2008-06-15 |  |  | #DIV/0!
2008-09-15 |  |  | #DIV/0!
2008-12-15 |  |  | #DIV/0!
Stratification Measure #1 | % Hi-Volume PCPs
Description of measure | % of PCPS defined as high volume based on criteria of panel sizes on a 12 month average of 1,000 or more members as of 12/31/2005.
Population | High volume PCPs defined as PCPs with panels greater than average of 1000 members.
Numerator | PCPs with >100 preventive visits per year
Denominator | # of PCPs performing preventive visits in members age 6-36 months
Are the data in the numerator cumlative over time (yes/no)? |  |  | Yes | Are the data in the denominator cumlative over time (yes/no)? | Yes
Data Source |  |  | Provider database for FHP-NJ.
Notes regarding the data for this measure: |  |  | Same data source for NJ DOHSS reporting.
Pilot population
Report Date | Numerator (number) | Denominator (number) | Rate or results
2006-04-15 | 95 | 200 | 47.5%
2006-06-15 | 89 | 205 | 43.41%
2006-08-15 | 125 | 202 | 61.88%
2006-10-15 | 112 | 199 | 56.28%
2006-12-15 |  |  | #DIV/0!
2007-03-15 |  |  | #DIV/0!
2007-06-15 |  |  | #DIV/0!
2007-09-15 |  |  | #DIV/0!
2007-12-15 |  |  | #DIV/0!
2008-03-15 |  |  | #DIV/0!
2008-06-15 |  |  | #DIV/0!
2008-09-15 |  |  | #DIV/0!
2008-12-15 |  |  | #DIV/0!
Stratification Measure #2 | % Hi-Opportunity PCPs
Description of measure | % of PCPS defined as high opportunity based on criteria of <50% of preventive visits with documentation of SDS administration.
Population | High volume PCPs defined as PCPs with panels greater than average of 1000 members.
Numerator | PCPs with fewer than 50% of preventive visits with SDS
Denominator | # of PCPs performing preventive visits in members age 6-36 months
Are the data in the numerator cumlative over time (yes/no)? |  |  | No | Are the data in the denominator cumlative over time (yes/no)? | No
Data Source |  |  | Medical claims data from the EPIPHYS claims system.
Notes regarding the data for this measure: |  |  | 3 month lag for 99% completeness of submitted claims from providers.
Pilot population
Report Date | Numerator (number) | Denominator (number) | Rate or results
2006-04-15 | 115 | 125 | 92%
2006-06-15 | 116 | 125 | 92.8%
2006-08-15 | 118 | 125 | 94.4%
2006-10-15 | 117 | 125 | 93.6%
2006-12-15 |  |  | #DIV/0!
2007-03-15 |  |  | #DIV/0!
2007-06-15 |  |  | #DIV/0!
2007-09-15 |  |  | #DIV/0!
2007-12-15 |  |  | #DIV/0!
2008-03-15 |  |  | #DIV/0!
2008-06-15 |  |  | #DIV/0!
2008-09-15 |  |  | #DIV/0!
2008-12-15 |  |  | #DIV/0!
Stratification Measure #3 | % Hi-Leverage PCPs
Description of measure | % of hi-leverage PCPs, as defined in numerator and denominator descriptions on Pilot Planning Tool tab.
Population | Integration of provider database and case management information to identify hi-leverage PCPs
Numerator | # of PCPs that are both Hi-Volume and Hi-Opportunity
Denominator | # of PCPs performing preventive visits in members age 6-36 months
Are the data in the numerator cumlative over time (yes/no)? |  |  | Yes | Are the data in the denominator cumlative over time (yes/no)? | Yes
Data Source |  |  | Medical claims data from the EPIPHYS claims system, FHP-NJ provider database.
Notes regarding the data for this measure: |  |  | claims lag will impact integration with provider database.
Pilot population
Report Date | Numerator (number) | Denominator (number) | Rate or results
2006-04-15 | 25 | 75 | 33.33%
2006-06-15 | 35 | 75 | 46.67%
2006-08-15 | 45 | 75 | 60%
2006-10-15 | 47 | 75 | 62.67%
2006-12-15 |  |  | #DIV/0!
2007-03-15 |  |  | #DIV/0!
2007-06-15 |  |  | #DIV/0!
2007-09-15 |  |  | #DIV/0!
2007-12-15 |  |  | #DIV/0!
2008-03-15 |  |  | #DIV/0!
2008-06-15 |  |  | #DIV/0!
2008-09-15 |  |  | #DIV/0!
2008-12-15 |  |  | #DIV/0!
Outreach Measure #1 | % of Hi-Leverage providers receiving educational in-service
Description of measure | % of providers in target population that were provided academic detailing regarding SDS administration.
Population | Providers in target population that were provided academic detailing regarding SDS administration.
Numerator | # of Hi-Leverage providers receiving educational in-service
Denominator | # of hi-leverage providers
Are the data in the numerator cumlative over time (yes/no)? |  |  | Yes | Are the data in the denominator cumlative over time (yes/no)? | Yes
Data Source |  |  | Provider relations database for tracking academic detailing activities.
Notes regarding the data for this measure: |  |  | database to be developed by IT department
Pilot population
Report Date | Numerator (number) | Denominator (number) | Rate or results
2006-04-15 | 15 | 60 | 25%
2006-06-15 | 28 | 60 | 46.67%
2006-08-15 | 31 | 60 | 51.67%
2006-10-15 | 35 | 60 | 58.33%
2006-12-15 |  |  | #DIV/0!
2007-03-15 |  |  | #DIV/0!
2007-06-15 |  |  | #DIV/0!
2007-09-15 |  |  | #DIV/0!
2007-12-15 |  |  | #DIV/0!
2008-03-15 |  |  | #DIV/0!
2008-06-15 |  |  | #DIV/0!
2008-09-15 |  |  | #DIV/0!
2008-12-15 |  |  | #DIV/0!
Outreach Measure #2 | n/a
Description of measure
Population
Numerator | n/a
Denominator | n/a
Are the data in the numerator cumlative over time (yes/no)? |  |  |  | Are the data in the denominator cumlative over time (yes/no)?
Data Source
Notes regarding the data for this measure:
Pilot population
Report Date | Numerator (number) | Denominator (number) | Rate or results
2006-04-15 |  |  | #DIV/0!
2006-06-15 |  |  | #DIV/0!
2006-08-15 |  |  | #DIV/0!
2006-10-15 |  |  | #DIV/0!
2006-12-15 |  |  | #DIV/0!
2007-03-15 |  |  | #DIV/0!
2007-06-15 |  |  | #DIV/0!
2007-09-15 |  |  | #DIV/0!
2007-12-15 |  |  | #DIV/0!
2008-03-15 |  |  | #DIV/0!
2008-06-15 |  |  | #DIV/0!
2008-09-15 |  |  | #DIV/0!
2008-12-15 |  |  | #DIV/0!
Outreach Measure #3 | n/a
Description of measure
Population
Numerator | n/a
Denominator | n/a
Are the data in the numerator cumlative over time (yes/no)? |  |  |  | Are the data in the denominator cumlative over time (yes/no)?
Data Source
Notes regarding the data for this measure:
Pilot population
Report Date | Numerator (number) | Denominator (number) | Rate or results
2006-04-15 |  |  | #DIV/0!
2006-06-15 |  |  | #DIV/0!
2006-08-15 |  |  | #DIV/0!
2006-10-15 |  |  | #DIV/0!
2006-12-15 |  |  | #DIV/0!
2007-03-15 |  |  | #DIV/0!
2007-06-15 |  |  | #DIV/0!
2007-09-15 |  |  | #DIV/0!
2007-12-15 |  |  | #DIV/0!
2008-03-15 |  |  | #DIV/0!
2008-06-15 |  |  | #DIV/0!
2008-09-15 |  |  | #DIV/0!
2008-12-15 |  |  | #DIV/0!
Intervention Measure #1 | SDS screening Rate for Hi-Leverage providers
Description of measure | Providers providing more than 50% SDS screening rate per measurement/reporting period.
Population | Target provider population.
Numerator | # of hi-leverage PCPs with 50% or higher rate for SDS
Denominator | # of hi-leverage PCPs
Are the data in the numerator cumlative over time (yes/no)? |  |  | Yes | Are the data in the denominator cumlative over time (yes/no)? | Yes
Data Source |  |  | Medical claims data from the EPIPHYS claims system.
Notes regarding the data for this measure: |  |  | 3 month lag for 99% completeness of submitted claims from providers.
Pilot population
Report Date | Numerator (number) | Denominator (number) | Rate or results
2006-04-15 | 10 | 60 | 16.67%
2006-06-15 | 11 | 60 | 18.33%
2006-08-15 | 11 | 60 | 18.33%
2006-10-15 | 13 | 60 | 21.67%
2006-12-15 |  |  | #DIV/0!
2007-03-15 |  |  | #DIV/0!
2007-06-15 |  |  | #DIV/0!
2007-09-15 |  |  | #DIV/0!
2007-12-15 |  |  | #DIV/0!
2008-03-15 |  |  | #DIV/0!
2008-06-15 |  |  | #DIV/0!
2008-09-15 |  |  | #DIV/0!
2008-12-15 |  |  | #DIV/0!
Intervention Measure #2 | n/a
Description of measure
Population
Numerator | n/a
Denominator | n/a
Are the data in the numerator cumlative over time (yes/no)? |  |  |  | Are the data in the denominator cumlative over time (yes/no)?
Data Source
Notes regarding the data for this measure:
Pilot population
Report Date | Numerator (number) | Denominator (number) | Rate or results
2006-04-15 |  |  | #DIV/0!
2006-06-15 |  |  | #DIV/0!
2006-08-15 |  |  | #DIV/0!
2006-10-15 |  |  | #DIV/0!
2006-12-15 |  |  | #DIV/0!
2007-03-15 |  |  | #DIV/0!
2007-06-15 |  |  | #DIV/0!
2007-09-15 |  |  | #DIV/0!
2007-12-15 |  |  | #DIV/0!
2008-03-15 |  |  | #DIV/0!
2008-06-15 |  |  | #DIV/0!
2008-09-15 |  |  | #DIV/0!
2008-12-15 |  |  | #DIV/0!
Intervention Measure #3 | n/a
Description of measure
Population
Numerator | n/a
Denominator | n/a
Are the data in the numerator cumlative over time (yes/no)? |  |  |  | Are the data in the denominator cumlative over time (yes/no)?
Data Source
Notes regarding the data for this measure:
Pilot population
Report Date | Numerator (number) | Denominator (number) | Rate or results
2006-04-15 |  |  | #DIV/0!
2006-06-15 |  |  | #DIV/0!
2006-08-15 |  |  | #DIV/0!
2006-10-15 |  |  | #DIV/0!
2006-12-15 |  |  | #DIV/0!
2007-03-15 |  |  | #DIV/0!
2007-06-15 |  |  | #DIV/0!
2007-09-15 |  |  | #DIV/0!
2007-12-15 |  |  | #DIV/0!
2008-03-15 |  |  | #DIV/0!
2008-06-15 |  |  | #DIV/0!
2008-09-15 |  |  | #DIV/0!
2008-12-15 |  |  | #DIV/0!
Overall Aim Measure #1 | % of high-leverage providers performing SDS
Description of measure | Rate of providers serving the target population who administer the standardized developmental screening (SDS) in children, age 6-36 months, during preventive visits.
Population | Providers serving the population of children, age 6-36 months.
Numerator | Providers serving the population of children, age 6-36 months administering the SDS in children.
Denominator | Targeted providers serving the population of children, age 6-36 months.
Are the data in the numerator cumlative over time (yes/no)? |  |  | Yes | Are the data in the denominator cumlative over time (yes/no)? | Yes
Data Source |  |  | Case management system
Notes regarding the data for this measure: |  |  | Data not from claims system, but case management department
Pilot population
Report Date | Numerator (number) | Denominator (number) | Rate or results
2006-04-15 | 10 | 60 | 16.67%
2006-06-15 | 11 | 60 | 18.33%
2006-08-15 | 11 | 60 | 18.33%
2006-10-15 | 12 | 60 | 20%
2006-12-15 |  |  | #DIV/0!
2007-03-15 |  |  | #DIV/0!
2007-06-15 |  |  | #DIV/0!
2007-09-15 |  |  | #DIV/0!
2007-12-15 |  |  | #DIV/0!
2008-03-15 |  |  | #DIV/0!
2008-06-15 |  |  | #DIV/0!
2008-09-15 |  |  | #DIV/0!
2008-12-15 |  |  | #DIV/0!
Overall Aim Measure #2 | % of ALL providers performing SDS
Description of measure | Rate of providers serving the target population who administer the standardized developmental screening (SDS) in children, age 6-36 months, during preventive visits.
Population | Providers serving the population of children, age 6-36 months.
Numerator | Providers serving the population of children, age 6-36 months administering the SDS in children.
Denominator | ALL providers serving the population of children, age 6-36 months.
Are the data in the numerator cumlative over time (yes/no)? |  |  | Yes | Are the data in the denominator cumlative over time (yes/no)? | Yes
Data Source |  |  | Medical claims system
Notes regarding the data for this measure: |  |  | 3 month lag for 99% completed/submitted claims.
Pilot population
Report Date | Numerator (number) | Denominator (number) | Rate or results
2006-04-15 | 39 | 453 | 8.609%
2006-06-15 | 45 | 453 | 9.934%
2006-08-15 | 46 | 453 | 10.15%
2006-10-15 | 45 | 453 | 9.934%
2006-12-15 |  |  | #DIV/0!
2007-03-15 |  |  | #DIV/0!
2007-06-15 |  |  | #DIV/0!
2007-09-15 |  |  | #DIV/0!
2007-12-15 |  |  | #DIV/0!
2008-03-15 |  |  | #DIV/0!
2008-06-15 |  |  | #DIV/0!
2008-09-15 |  |  | #DIV/0!
2008-12-15 |  |  | #DIV/0!
Overall Aim Measure #3 | Enter the name of the measure on the Pilot Planning Tool Tab
Description of measure | Enter this descriptive information on the Pilot Planning Tool Tab
Population | Enter this descriptive information on the Pilot Planning Tool Tab
Numerator | Enter this descriptive information on the Pilot Planning Tool Tab
Denominator | Enter this descriptive information on the Pilot Planning Tool Tab
Are the data in the numerator cumlative over time (yes/no)? |  |  |  | Are the data in the denominator cumlative over time (yes/no)?
Data Source
Notes regarding the data for this measure:
Pilot population
Report Date | Numerator (number) | Denominator (number) | Rate or results
2006-04-15 |  |  | #DIV/0!
2006-06-15 |  |  | #DIV/0!
2006-08-15 |  |  | #DIV/0!
2006-10-15 |  |  | #DIV/0!
2006-12-15 |  |  | #DIV/0!
2007-03-15 |  |  | #DIV/0!
2007-06-15 |  |  | #DIV/0!
2007-09-15 |  |  | #DIV/0!
2007-12-15 |  |  | #DIV/0!
2008-03-15 |  |  | #DIV/0!
2008-06-15 |  |  | #DIV/0!
2008-09-15 |  |  | #DIV/0!
2008-12-15 |  |  | #DIV/0!
Overall Aim Measure #4 | Enter the name of the measure on the Pilot Planning Tool Tab
Description of measure | Enter this descriptive information on the Pilot Planning Tool Tab
Population | Enter this descriptive information on the Pilot Planning Tool Tab
Numerator | Enter this descriptive information on the Pilot Planning Tool Tab
Denominator | Enter this descriptive information on the Pilot Planning Tool Tab
Are the data in the numerator cumlative over time (yes/no)? |  |  |  | Are the data in the denominator cumlative over time (yes/no)?
Data Source
Notes regarding the data for this measure:
Pilot population
Report Date | Numerator (number) | Denominator (number) | Rate or results
2006-04-15 |  |  | #DIV/0!
2006-06-15 |  |  | #DIV/0!
2006-08-15 |  |  | #DIV/0!
2006-10-15 |  |  | #DIV/0!
2006-12-15 |  |  | #DIV/0!
2007-03-15 |  |  | #DIV/0!
2007-06-15 |  |  | #DIV/0!
2007-09-15 |  |  | #DIV/0!
2007-12-15 |  |  | #DIV/0!
2008-03-15 |  |  | #DIV/0!
2008-06-15 |  |  | #DIV/0!
2008-09-15 |  |  | #DIV/0!
2008-12-15 |  |  | #DIV/0!
Note on A17: First report date is BASELINE data.
Note on A52: First report date is BASELINE data.
Note on A87: First report date is BASELINE data.
Note on A122: First report date is BASELINE data.
Note on A157: First report date is BASELINE data.
Note on A192: First report date is BASELINE data.
Note on A227: First report date is BASELINE data.
Note on A262: First report date is BASELINE data.
Note on A297: First report date is BASELINE data.
Note on A332: First report date is BASELINE data.
Note on A367: First report date is BASELINE data.
Note on E17: Please do not place your data in these cells if the Report Date cells are blank.
Note on E52: Please do not place your data in these cells if the Report Date cells are blank.
Note on E87: Please do not place your data in these cells if the Report Date cells are blank.
Note on E122: Please do not place your data in these cells if the Report Date cells are blank.
Note on E157: Please do not place your data in these cells if the Report Date cells are blank.
Note on E192: Please do not place your data in these cells if the Report Date cells are blank.
Note on E227: Please do not place your data in these cells if the Report Date cells are blank.
Note on E262: Please do not place your data in these cells if the Report Date cells are blank.
Note on E297: Please do not place your data in these cells if the Report Date cells are blank.
Note on E332: Please do not place your data in these cells if the Report Date cells are blank.
Note on E367: Please do not place your data in these cells if the Report Date cells are blank.
Note on E402: Please do not place your data in these cells if the Report Date cells are blank.
Note on E437: Please do not place your data in these cells if the Report Date cells are blank.
Note on E472: Please do not place your data in these cells if the Report Date cells are blank.
Note on E507: Please do not place your data in these cells if the Report Date cells are blank.
EXAMPLE
BCAP Quality
Workbook
EXAMPLE
BCAP Quality
Workbook
EXAMPLE
BCAP Quality
Workbook
EXAMPLE
BCAP Quality
Workbook
EXAMPLE
BCAP Quality
Workbook
EXAMPLE
BCAP Quality
Workbook
EXAMPLE
BCAP Quality
Workbook
EXAMPLE
BCAP Quality
Workbook
EXAMPLE
BCAP Quality
Workbook
EXAMPLE
BCAP Quality
Workbook
EXAMPLE
BCAP Quality
Workbook
EXAMPLE
BCAP Quality
Workbook
EXAMPLE
BCAP Quality
Workbook
EXAMPLE
BCAP Quality
Workbook
EXAMPLE
BCAP Quality
Workbook

## EXAMPLE Pilot Measure Graphs
Organization Name: | Health Plan of NJ | Organization Name: | Health Plan of NJ
Identification measure #1 | Percent of preventive visits for members age 6-36 months assessed with SDS. | Identification measure #2 | % of PCPs performing preventive visits in members age 6-36 months
Description of measure | Claims data using CPT codes to identify preventive visits for members age 6 to 36 months. Age based on end of reporting time period. CPT codes are: 99290,99291, 99292,99293, 99295. | Description of measure | Filtered by provider ID#. Claims data using CPT codes to identify preventive visits for members age 6 to 36 months. Age based on end of reporting time period. CPT codes are: 99290,99291, 99292,99293, 99295.
Population | All members age 6-36 months. | Population | All PCPs for members age 6-36 months.
Numerator | # of preventive visit for members age 6-36 month with SDS | Numerator | # of PCPs performing preventive visits in members age 6-36 months
Denominator | # of preventive visits for members age 6-36 months | Denominator | ALL providers serving the population of children, age 6-36 months.
Organization Name: | Health Plan of NJ | Organization Name: | Health Plan of NJ
Stratification Measure #1 | % Hi-Volume PCPs | Stratification Measure #2 | % Hi-Opportunity PCPs
Description of measure | % of PCPS defined as high volume based on criteria of panel sizes on a 12 month average of 1,000 or more members as of 12/31/2005. | Description of measure | % of PCPS defined as high opportunity based on criteria of <50% of preventive visits with documentation of SDS administration.
Population | High volume PCPs defined as PCPs with panels greater than average of 1000 members. | Population | High volume PCPs defined as PCPs with panels greater than average of 1000 members.
Numerator | PCPs with >100 preventive visits per year | Numerator | PCPs with fewer than 50% of preventive visits with SDS
Denominator | # of PCPs performing preventive visits in members age 6-36 months | Denominator | # of PCPs performing preventive visits in members age 6-36 months
Organization Name: | Health Plan of NJ | Organization Name: | Health Plan of NJ
Stratification Measure #3 | % Hi-Leverage PCPs | Outreach Measure #1 | % of Hi-Leverage providers receiving educational in-service
Description of measure | % of hi-leverage PCPs, as defined in numerator and denominator descriptions on Pilot Planning Tool tab. | Description of measure | % of providers in target population that were provided academic detailing regarding SDS administration.
Population | Integration of provider database and case management information to identify hi-leverage PCPs | Population | Providers in target population that were provided academic detailing regarding SDS administration.
Numerator | # of PCPs that are both Hi-Volume and Hi-Opportunity | Numerator | # of Hi-Leverage providers receiving educational in-service
Denominator | # of PCPs performing preventive visits in members age 6-36 months | Denominator | # of hi-leverage providers
Organization Name: | Health Plan of NJ | Organization Name: | Health Plan of NJ
Outreach Measure #2 | n/a | Outreach Measure #3 | n/a
Description of measure | 0 | Description of measure | 0
Population | 0 | Population | 0
Numerator | n/a | Numerator | n/a
Denominator | n/a | Denominator | n/a
Organization Name: | Health Plan of NJ | Organization Name: | Health Plan of NJ
Intervention Measure #1 | SDS screening Rate for Hi-Leverage providers | Intervention Measure #2 | n/a
Description of measure | Providers providing more than 50% SDS screening rate per measurement/reporting period. | Description of measure | 0
Population | Target provider population. | Population | 0
Numerator | # of hi-leverage PCPs with 50% or higher rate for SDS | Numerator | n/a
Denominator | # of hi-leverage PCPs | Denominator | n/a
Organization Name: | Health Plan of NJ | Organization Name: | Health Plan of NJ
Intervention Measure #3 | n/a | Overall Aim Measure #1 | % of high-leverage providers performing SDS
Description of measure | 0 | Description of measure | Rate of providers serving the target population who administer the standardized developmental screening (SDS) in children, age 6-36 months, during preventive visits.
Population | 0 | Population | Providers serving the population of children, age 6-36 months.
Numerator | n/a | Numerator | Providers serving the population of children, age 6-36 months administering the SDS in children.
Denominator | n/a | Denominator | Targeted providers serving the population of children, age 6-36 months.
Organization Name: | Health Plan of NJ | Organization Name: | Health Plan of NJ
Overall Aim Measure #2 | % of ALL providers performing SDS | Overall Aim Measure #3 | Enter the name of the measure on the Pilot Planning Tool Tab
Description of measure | Rate of providers serving the target population who administer the standardized developmental screening (SDS) in children, age 6-36 months, during preventive visits. | Description of measure | Enter this descriptive information on the Pilot Planning Tool Tab
Population | Providers serving the population of children, age 6-36 months. | Population | Enter this descriptive information on the Pilot Planning Tool Tab
Numerator | Providers serving the population of children, age 6-36 months administering the SDS in children. | Numerator | Enter this descriptive information on the Pilot Planning Tool Tab
Denominator | ALL providers serving the population of children, age 6-36 months. | Denominator | Enter this descriptive information on the Pilot Planning Tool Tab
Organization Name: | Health Plan of NJ
Overall Aim Measure #4 | Enter the name of the measure on the Pilot Planning Tool Tab
Description of measure | Enter this descriptive information on the Pilot Planning Tool Tab
Population | Enter this descriptive information on the Pilot Planning Tool Tab
Numerator | Enter this descriptive information on the Pilot Planning Tool Tab
Denominator | Enter this descriptive information on the Pilot Planning Tool Tab
EXAMPLE
BCAP Quality
Workbook
EXAMPLE
BCAP Quality
Workbook
EXAMPLE
BCAP Quality
Workbook
EXAMPLE
BCAP Quality
Workbook
EXAMPLE
BCAP Quality
Workbook
EXAMPLE
BCAP Quality
Workbook

## EXAMPLE Assessment Scales
Title: | Children's Futures BCAP
Organization Name: | Health Plan of NJ
Contact Name: | Susan Smith
Contact Phone Number: | 609-528-8400
Submission Date: | 2006-06-15
Report Date | Team Assessment Scale | Sustainability Scale | Diffusion Scale
2006-04-15 | 1 | 1 | 1
2006-06-15 | 4 | 2 | 1
2006-08-15
2006-10-15
2006-12-15
Instructions: Please complete this form each quarter as part of your team's quarterly report. Use the the 7-point scale (refer to the comment in cell B7) and determine which score on the scale best describes your team's functional level for the current reporting quarter. Record the corresponding number in the cell corresponding the the reporting quarter. You may wish to ask each team member to assess the team's performance level individually and average those scores for your report. | Team Assessment Definitions: 1=Team Formed Appropriate stakeholders are represented Team leadership identified Team roles established 2=Team Goals Established Team has identified collective goal(s) Team has developed an action plan 3=Team Activity, No Change Team has met regularly within last quarter Team has discussed the change(s) they want to make Team has written an implementation plan with each member’s contribution identified 4=Pilot Effort Underway Team has identified each member’s contributions to the change activity Team has implemented change activity Team has measured change activity 5=Pilot Effort Evaluation Team has met to debrief on the initial pilot change activity and measurements All team members understand the results of the change activity Each team member’s contribution has been documented Team has identified next steps in modifying and improving the change activity 6=Change Has Occurred Team can demonstrate through measurement that change has occurred 7=Change Can Be Sustained Team can demonstrate that a structure or process has been institutionalized so that the change can be sustained over time.
Sustainability Scale Definitions: 1=No Effort No movement toward long-term sustainability 2=Minimal Effort Efforts made to research how to ensure sustainability by obtaining funding and/or changing processes, structures or policies 3=Active Efforts Attempts made to obtain funding and/or change processes, structures or policies to ensure sustainability 4=Limited Sustainability Effort has secured temporary funding and/or changes in process, structure or policies have been temporarily instituted; however, the duration and comprehensiveness of the effort are unclear 5=Successfully Sustained Project has secured long-term funding, and/or has been institutionalized by changes in process, structure, or policies |  | Diffusion Scale Definitions: 1=Spreading the Word Publications describing the best practice. Additional promotion (e.g., website, media, newsletters) describing the best practice 2=Direct Contact Responding to a request for information about the best practice. Presentations describing the best practice (e.g., teleconferences, meetings, list serve) 3=Training Formal training of one or more people in the best practice. Presenting at CHCS Workshops or Technical Assistance 4=Mentoring Mentoring is being provided to a new team which has been formed and has undertaken a replication of the best practice 5=Successful Diffusion One or more teams have been formed and have successfully replicated the best practice.
Note on A7: Instructions: Please complete this form each quarter as part of your team's quarterly report. Use the the 7-point scale (refer to the comment in cell B7) and determine which score on the scale best describes your team's functional level for the current reporting quarter. Record the corresponding number in the cell corresponding the the reporting quarter. You may wish to ask each team member to assess the team's performance level individually and average those scores for your report.
Note on B7: Team Assessment Definitions: 1=Team Formed Appropriate stakeholders are represented Team leadership identified Team roles established 2=Team Goals Established Team has identified collective goal(s) Team has developed an action plan 3=Team Activity, No Change Team has met regularly within last quarter Team has discussed the change(s) they want to make Team has written an implementation plan with each member’s contribution identified 4=Pilot Effort Underway Team has identified each member’s contributions to the change activity Team has implemented change activity Team has measured change activity 5=Pilot Effort Evaluation Team has met to debrief on the initial pilot change activity and measurements All team members understand the results of the change activity Each team member’s contribution has been documented Team has identified next steps in modifying and improving the change activity 6=Change Has Occurred Team can demonstrate through measurement that change has occurred 7=Change Can Be Sustained Team can demonstrate that a structure or process has been nstitutionalized so that the change can be sustained over time.
Note on B8: Please Record one number in the cell for your current reporting date. Use this scale: 1 = Team formed 2 = Team goals established 3 = Team activity, no change 4 = Pilot effort underway 5 = Pilot effort evaluation 6 = Change has occurred 7 = Change can be sustained
Note on B9: Please Record one number in the cell for your current reporting date. Use this scale: 1 = Team formed 2 = Team goals established 3 = Team activity, no change 4 = Pilot effort underway 5 = Pilot effort evaluation 6 = Change has occurred 7 = Change can be sustained
Note on B10: Please Record one number in the cell for your current reporting date. Use this scale: 1 = Team formed 2 = Team goals established 3 = Team activity, no change 4 = Pilot effort underway 5 = Pilot effort evaluation 6 = Change has occurred 7 = Change can be sustained
Note on B11: Please Record one number in the cell for your current reporting date. Use this scale: 1 = Team formed 2 = Team goals established 3 = Team activity, no change 4 = Pilot effort underway 5 = Pilot effort evaluation 6 = Change has occurred 7 = Change can be sustained
Note on B12: Please Record one number in the cell for your current reporting date. Use this scale: 1 = Team formed 2 = Team goals established 3 = Team activity, no change 4 = Pilot effort underway 5 = Pilot effort evaluation 6 = Change has occurred 7 = Change can be sustained
Note on B13: Please Record one number in the cell for your current reporting date. Use this scale: 1 = Team formed 2 = Team goals established 3 = Team activity, no change 4 = Pilot effort underway 5 = Pilot effort evaluation 6 = Change has occurred 7 = Change can be sustained
Note on B14: Please Record one number in the cell for your current reporting date. Use this scale: 1 = Team formed 2 = Team goals established 3 = Team activity, no change 4 = Pilot effort underway 5 = Pilot effort evaluation 6 = Change has occurred 7 = Change can be sustained
Note on B15: Please Record one number in the cell for your current reporting date. Use this scale: 1 = Team formed 2 = Team goals established 3 = Team activity, no change 4 = Pilot effort underway 5 = Pilot effort evaluation 6 = Change has occurred 7 = Change can be sustained
Note on C7: Sustainability Scale Definitions: 1=No Effort No movement toward long-term sustainability 2=Minimal Effort Efforts made to research how to ensure sustainability by obtaining funding and/or changing processes, structures or policies 3=Active Efforts Attempts made to obtain funding and/or change processes, structures or policies to ensure sustainability 4=Limited Sustainability Effort has secured temporary funding and/or changes in process, structure or policies have been temporarily instituted; however, the duration and comprehensiveness of the effort are unclear 5=Successfully Sustained Project has secured long-term funding, and/or has been institutionalized by changes in process, structure, or policies
Note on C8: Please record one number in the cell for your current reporting date. Use this scale: 1 = No Effort 2 = Minimal Effort 3 = Active Efforts 4 = Limited Sustainability 5 = Successfully Sustained
Note on C9: Please record one number in the cell for your current reporting date. Use this scale: 1 = No Effort 2 = Minimal Effort 3 = Active Efforts 4 = Limited Sustainability 5 = Successfully Sustained
Note on C10: Please record one number in the cell for your current reporting date. Use this scale: 1 = No Effort 2 = Minimal Effort 3 = Active Efforts 4 = Limited Sustainability 5 = Successfully Sustained
Note on C11: Please record one number in the cell for your current reporting date. Use this scale: 1 = No Effort 2 = Minimal Effort 3 = Active Efforts 4 = Limited Sustainability 5 = Successfully Sustained
Note on C12: Please record one number in the cell for your current reporting date. Use this scale: 1 = No Effort 2 = Minimal Effort 3 = Active Efforts 4 = Limited Sustainability 5 = Successfully Sustained
Note on C13: Please record one number in the cell for your current reporting date. Use this scale: 1 = No Effort 2 = Minimal Effort 3 = Active Efforts 4 = Limited Sustainability 5 = Successfully Sustained
Note on C14: Please record one number in the cell for your current reporting date. Use this scale: 1 = No Effort 2 = Minimal Effort 3 = Active Efforts 4 = Limited Sustainability 5 = Successfully Sustained
Note on C15: Please record one number in the cell for your current reporting date. Use this scale: 1 = No Effort 2 = Minimal Effort 3 = Active Efforts 4 = Limited Sustainability 5 = Successfully Sustained
Note on D7: Diffusion Scale Definitions: 1=Spreading the Word Publications describing the best practice. Additional promotion (e.g., website, media, newsletters) describing the best practice 2=Direct Contact Responding to a request for information about the best practice. Presentations describing the best practice (e.g., teleconferences, meetings, list serve) 3=Training Formal training of one or more people in the best practice. Presenting at CHCS Workshops or Technical Assistance 4=Mentoring Mentoring is being provided to a new team which has been formed and has undertaken a replication of the best practice 5=Successful Diffusion One or more teams have been formed and have successfully replicated the best practice.
Note on D8: Please record one number in the cell for your current reporting date. Use this scale: 1 = Spreading the word 2 = Direct contact 3 = Training 4 = Mentoring 5 = Successful Diffusion
Note on D9: Please record one number in the cell for your current reporting date. Use this scale: 1 = Spreading the word 2 = Direct contact 3 = Training 4 = Mentoring 5 = Successful Diffusion
Note on D10: Please record one number in the cell for your current reporting date. Use this scale: 1 = Spreading the word 2 = Direct contact 3 = Training 4 = Mentoring 5 = Successful Diffusion
Note on D11: Please record one number in the cell for your current reporting date. Use this scale: 1 = Spreading the word 2 = Direct contact 3 = Training 4 = Mentoring 5 = Successful Diffusion
Note on D12: Please record one number in the cell for your current reporting date. Use this scale: 1 = Spreading the word 2 = Direct contact 3 = Training 4 = Mentoring 5 = Successful Diffusion
Note on D13: Please record one number in the cell for your current reporting date. Use this scale: 1 = Spreading the word 2 = Direct contact 3 = Training 4 = Mentoring 5 = Successful Diffusion
Note on D14: Please record one number in the cell for your current reporting date. Use this scale: 1 = Spreading the word 2 = Direct contact 3 = Training 4 = Mentoring 5 = Successful Diffusion
Note on D15: Please record one number in the cell for your current reporting date. Use this scale: 1 = Spreading the word 2 = Direct contact 3 = Training 4 = Mentoring 5 = Successful Diffusion
EXAMPLE
BCAP Quality
Workbook

## EXAMPLE Common Measures Report
|  |  |  | COMMON MEASURES |  | Yes
No
Title: |  | Children's Futures BCAP
Organization Name: |  | Health Plan of NJ
Contact Name: |  | Susan Smith
Contact Phone Number: |  | 609-528-8400
Submission Date: |  | 2006-06-15
Common Measure #1 | % providers submitting 4P's PLUS assessments.
Description of measure | % of providers in network submitting 4P's PLUS assessments performed for parents/guardians of members ages 6-36 months.
Population | All providers serving members ages 6-36 months.
Numerator | Providers administering 4P's Plus assessment during the prior 3-month time period.
Denominator | All providers serving members ages 6-36 months.
Are the data in the numerator cumlative over time (yes/no)? |  |  | Yes | Are the data in the denominator cumlative over time (yes/no)? | Yes
Notes regarding the data for this measure: |  |  | Dependent upon providers completing and submitting 4P's Plus assessment forms.
Common measure population
Report Date | Numerator (number) | Denominator (number) | Rate or results
2006-08-15 | 12 | 453 | 2.649%
2006-10-15 | 18 | 453 | 3.974%
2006-12-15 |  |  | #DIV/0!
2007-03-15 |  |  | #DIV/0!
2007-06-15 |  |  | #DIV/0!
2007-09-15 |  |  | #DIV/0!
2007-12-15 |  |  | #DIV/0!
2008-03-15 |  |  | #DIV/0!
2008-06-15 |  |  | #DIV/0!
2008-09-15 |  |  | #DIV/0!
2008-12-15 |  |  | #DIV/0!
Common Measure #2 | % of referrals to substance abuse treatment services for persons completing 4P's PLUS assessments.
Description of measure | How many members for whom an assessment is performed are referred to treatment services.
Population | All parents/guardians of children age 6-36 months who are assessed using the SDS by providers.
Numerator | Number of parents/guardians who are referred for SA treatment services.
Denominator | Number of parents/guardians who are assessed using SDS assessment.
Are the data in the numerator cumlative over time (yes/no)? |  |  | Yes | Are the data in the denominator cumlative over time (yes/no)? | Yes
Notes regarding the data for this measure: |  |  | Dependent upon providers completing and submitting 4P's Plus assessment forms.
Common measure population
Report Date | Numerator (number) | Denominator (number) | Rate or results
2006-08-15 | 153 | 598 | 25.59%
2006-10-15 | 168 | 645 | 26.05%
2006-12-15 | 201 | 802 | 25.06%
2007-03-15 | 216 | 912 | 23.68%
2007-06-15 |  |  | #DIV/0!
2007-09-15 |  |  | #DIV/0!
2007-12-15 |  |  | #DIV/0!
2008-03-15 |  |  | #DIV/0!
2008-06-15 |  |  | #DIV/0!
2008-09-15 |  |  | #DIV/0!
2008-12-15 |  |  | #DIV/0!
Common Measure #3 | Enter Name of Measure Here.
Description of measure
Population
Numerator
Denominator
Are the data in the numerator cumlative over time (yes/no)? |  |  |  | Are the data in the denominator cumlative over time (yes/no)?
Notes regarding the data for this measure:
Common measure population
Report Date | Numerator (number) | Denominator (number) | Rate or results
2006-08-15 |  |  | #DIV/0!
2006-10-15 |  |  | #DIV/0!
2006-12-15 |  |  | #DIV/0!
2007-03-15 |  |  | #DIV/0!
2007-06-15 |  |  | #DIV/0!
2007-09-15 |  |  | #DIV/0!
2007-12-15 |  |  | #DIV/0!
2008-03-15 |  |  | #DIV/0!
2008-06-15 |  |  | #DIV/0!
2008-09-15 |  |  | #DIV/0!
2008-12-15 |  |  | #DIV/0!
Note on A16: First report date is BASELINE data.
Note on A42: First report date is BASELINE data.
Note on A68: First report date is BASELINE data.
Note on E16: Please do not place your data in these cells if the Report Date cells are blank.
Note on E42: Please do not place your data in these cells if the Report Date cells are blank.
Note on E68: Please do not place your data in these cells if the Report Date cells are blank.
EXAMPLE
BCAP Quality
Workbook
EXAMPLE
BCAP Quality
Workbook
EXAMPLE
BCAP Quality
Workbook
EXAMPLE
BCAP Quality
Workbook

## EXAMPLE Common Measure Graphs
Organization Name: | Health Plan of NJ
Common Measure #1 | % providers submitting 4P's PLUS assessments.
Description of measure | % of providers in network submitting 4P's PLUS assessments performed for parents/guardians of members ages 6-36 months.
Population | All providers serving members ages 6-36 months.
Numerator | Providers administering 4P's Plus assessment during the prior 3-month time period.
Denominator | All providers serving members ages 6-36 months.
Organization Name: | Health Plan of NJ
Common Measure #2 | % of referrals to substance abuse treatment services for persons completing 4P's PLUS assessments.
Description of measure | How many members for whom an assessment is performed are referred to treatment services.
Population | All parents/guardians of children age 6-36 months who are assessed using the SDS by providers.
Numerator | Number of parents/guardians who are referred for SA treatment services.
Denominator | Number of parents/guardians who are assessed using SDS assessment.
Organization Name: | Health Plan of NJ
Common Measure #3 | Enter Name of Measure Here.
Description of measure | 0
Population | 0
Numerator | 0
Denominator | 0
Organization Name: | Health Plan of NJ
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
Organization Name: | Health Plan of NJ
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
Organization Name: | Health Plan of NJ
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
Organization Name: | Health Plan of NJ
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
Organization Name: | Health Plan of NJ
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
EXAMPLE
BCAP Quality
Workbook
EXAMPLE
BCAP Quality
Workbook