## Schedule of Reporting
BCAP® Quality Workbook
Title: | Project Title here
Organization Name: | On Schedule of Reporting tab, enter Organization/Plan/Practice Name
Contact Name: | On Schedule of Reporting tab, enter contact person's name
Contact Phone Number: | On Schedule of Reporting tab, enter phone number (with area code)
Submission Date: | On Schedule of Reporting tab, enter date (DD/MM/YY)
© 2006 Center for Health Care Strategies
Date Report Due | Project Measurement Form, PDSA Cycles by BCAP Category | Pilot Data Report* | Team Assessment | Sustainability and Diffusion Scales | Common Measures
2006-04-15 | Baseline | Baseline | Baseline
2006-06-15 | X | X | X
2006-08-15 | X | X | X | Baseline | Baseline
2006-10-15 | X | X | X | X | X
2006-12-15 | X | X | X | X | X
2007-03-15 |  |  |  |  | X
2007-06-15 |  |  |  |  | X
2007-09-15 |  |  |  |  | X
2007-12-15 |  |  |  |  | X
2008-03-15 |  |  |  |  | X
2008-06-15 |  |  |  |  | X
2008-09-15 |  |  |  |  | X
2008-12-15 |  |  |  |  | X
2009-03-15 |  |  |  |  | X
2009-06-15 |  |  |  |  | X
2009-09-15 |  |  |  |  | X
2009-12-15 |  |  |  |  | X
2010-03-15 |  |  |  |  | X
2010-06-15 |  |  |  |  | X
2010-09-15 |  |  |  |  | X
2010-12-15 |  |  |  |  | X
2011-03-15 |  |  |  |  | X
2011-06-15 |  |  |  |  | X
2011-09-15 |  |  |  |  | X
* - The Pilot Data Report allows space for monthly data collection by MCO.
PRINTING INSTRUCTIONS: All pages are oriented as 'portrait' for printing, with the exception of the Pilot Measure Graphs which are oriented 'landscape.'

## Pilot Planning Tool
Title: | Project Title here |  | Submission Date:
Organization Name: | On Schedule of Reporting tab, enter Organization/Plan/Practice Name |  | CHCS Approval Date:
Contact Name: | On Schedule of Reporting tab, enter contact person's name |  | Review Dates
Contact Phone Number: | On Schedule of Reporting tab, enter phone number (with area code)
Submission Date: | On Schedule of Reporting tab, enter date (DD/MM/YY)
Overall Project Aim
Typology Category | Identification | Stratification | Outreach | Intervention
Typology Aim (Please state quantitatively.)
Measure(s) for test of change: | Enter the name of the measure on the Pilot Planning Tool Tab | Enter the name of the measure on the Pilot Planning Tool Tab | Enter the name of the measure on the Pilot Planning Tool Tab | Enter the name of the measure on the Pilot Planning Tool Tab
Numerator | Enter this descriptive information on the Pilot Planning Tool Tab | Enter this descriptive information on the Pilot Planning Tool Tab | Enter this descriptive information on the Pilot Planning Tool Tab | Enter this descriptive information on the Pilot Planning Tool Tab
Denominator | Enter this descriptive information on the Pilot Planning Tool Tab | Enter this descriptive information on the Pilot Planning Tool Tab | Enter this descriptive information on the Pilot Planning Tool Tab | Enter this descriptive information on the Pilot Planning Tool Tab
Measure(s) for test of change: | Enter the name of the measure on the Pilot Planning Tool Tab | Enter the name of the measure on the Pilot Planning Tool Tab | Enter the name of the measure on the Pilot Planning Tool Tab | Enter the name of the measure on the Pilot Planning Tool Tab
Numerator | Enter this descriptive information on the Pilot Planning Tool Tab | Enter this descriptive information on the Pilot Planning Tool Tab | Enter this descriptive information on the Pilot Planning Tool Tab | Enter this descriptive information on the Pilot Planning Tool Tab
Denominator | Enter this descriptive information on the Pilot Planning Tool Tab | Enter this descriptive information on the Pilot Planning Tool Tab | Enter this descriptive information on the Pilot Planning Tool Tab | Enter this descriptive information on the Pilot Planning Tool Tab
Measure(s) for test of change: |  | Enter the name of the measure on the Pilot Planning Tool Tab | Enter the name of the measure on the Pilot Planning Tool Tab | Enter the name of the measure on the Pilot Planning Tool Tab
Numerator |  | Enter this descriptive information on the Pilot Planning Tool Tab | Enter this descriptive information on the Pilot Planning Tool Tab | Enter this descriptive information on the Pilot Planning Tool Tab
Denominator |  | Enter this descriptive information on the Pilot Planning Tool Tab | Enter this descriptive information on the Pilot Planning Tool Tab | Enter this descriptive information on the Pilot Planning Tool Tab
Description of the first change activity you will try: | PDSA 1: | PDSA 1: | PDSA 1: | PDSA 1:
PLAN
DO
STUDY
ACT
What is the target date for starting this change activity?
What barriers do you anticipate and what strategies will you use to address them?
What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this pilot activity?
What Technical Assistance (TA) do you need to be able to move forward?
Have any issues arisen with enrollment into or engagement of patients in the intervention?
Have any details of the intervention strategy changed since the last reporting period?
Overall Aim Measure #1 | Enter the name of the measure on the Pilot Planning Tool Tab
Description of measure | Enter this descriptive information on the Pilot Planning Tool Tab
Population | Enter this descriptive information on the Pilot Planning Tool Tab
Numerator | Enter this descriptive information on the Pilot Planning Tool Tab
Denominator | Enter this descriptive information on the Pilot Planning Tool Tab
Overall Aim Measure #2 | Enter the name of the measure on the Pilot Planning Tool Tab
Description of measure | Enter this descriptive information on the Pilot Planning Tool Tab
Population | Enter this descriptive information on the Pilot Planning Tool Tab
Numerator | Enter this descriptive information on the Pilot Planning Tool Tab
Denominator | Enter this descriptive information on the Pilot Planning Tool Tab
Overall Aim Measure #3 | Enter the name of the measure on the Pilot Planning Tool Tab
Description of measure | Enter this descriptive information on the Pilot Planning Tool Tab
Population | Enter this descriptive information on the Pilot Planning Tool Tab
Numerator | Enter this descriptive information on the Pilot Planning Tool Tab
Denominator | Enter this descriptive information on the Pilot Planning Tool Tab
Overall Aim Measure #4 | Enter the name of the measure on the Pilot Planning Tool Tab
Description of measure | Enter this descriptive information on the Pilot Planning Tool Tab
Population | Enter this descriptive information on the Pilot Planning Tool Tab
Numerator | Enter this descriptive information on the Pilot Planning Tool Tab
Denominator | Enter this descriptive information on the Pilot Planning Tool Tab
Note on B10: Begin with the end in mind. Are these pilot measures aligned to the desired outcome? If, not you might need to select other pilot measures that will lead to the final results.
Note on C10: Begin with the end in mind. Are these pilot measures aligned to the desired outcome? If, not you might need to select other pilot measures that will lead to the final results.
Note on D10: Begin with the end in mind. Are these pilot measures aligned to the desired outcome? If, not you might need to select other pilot measures that will lead to the final results.
Note on E10: Begin with the end in mind. Are these pilot measures aligned to the desired outcome? If, not you might need to select other pilot measures that will lead to the final results.

## PDSA Cycles
Plan, Do, Study, Act
Title: | Project Title here
Organization Name: | On Schedule of Reporting tab, enter Organization/Plan/Practice Name
Contact Name: | On Schedule of Reporting tab, enter contact person's name
Contact Phone Number: | On Schedule of Reporting tab, enter phone number (with area code)
Submission Date: | On Schedule of Reporting tab, enter date (DD/MM/YY)
The following questions should guide your thinking around changes/ improvements in your intervention. As you test these changes, please document your activities in the PDSA section below. The Test of Change reporting is structured to reinforce the use of Plan - Do - Study - Act iterative cycles (PDSA). Describe the change activities you plan on implementing or have already implemented. You may have multiple small tests of change to reach your aim by typology, as well as your overall project aim.
Be sure to consider these questions as you document your PDSA cycles: | What barriers do you anticipate and what strategies will you use to address them? | What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? | What Technical Assistance (TA) do you need to be able to move forward? | Have any issues arisen with enrollment into or engagement of patients in the intervention? | Have any details of the intervention strategy changed since the last reporting period?
Identification: PDSA Cycle #1 (Please enter information in the appropriate cells on the Pilot Planning Tool tab)
Date: | 0
Plan: | 0
Do: | 0
Study: | 0
Act: | 0
Identification: PDSA Cycle #2 (Please enter information in the appropriate cells below)
Date:
Plan:
Do:
Study:
Act:
Identification: PDSA Cycle #3 (Please enter information in the appropriate cells below)
Date:
Plan:
Do:
Study:
Act:
Stratification: PDSA Cycle #1 (Please enter information in the appropriate cells on the Pilot Planning Tool tab)
Date: | 0
Plan: | 0
Do: | 0
Study: | 0
Act: | 0
Stratification: PDSA Cycle #2 (Please enter information in the appropriate cells below)
Date:
Plan:
Do:
Study:
Act:
Stratification: PDSA Cycle #3 (Please enter information in the appropriate cells below)
Date:
Plan:
Do:
Study:
Act:
Outreach: PDSA Cycle #1 (Please enter information in the appropriate cells on the Pilot Planning Tool tab)
Date: | 0
Plan: | 0
Do: | 0
Study: | 0
Act: | 0
Outreach: PDSA Cycle #2 (Please enter information in the appropriate cells below)
Date:
Plan:
Do:
Study:
Act:
Outreach: PDSA Cycle #3 (Please enter information in the appropriate cells below)
Date:
Plan:
Do:
Study:
Act:
Intervention: PDSA Cycle #1 (Please enter information in the appropriate cells on the Pilot Planning Tool tab)
Date: | 0
Plan: | 0
Do: | 0
Study: | 0
Act: | 0
Intervention: PDSA Cycle #2 (Please enter information in the appropriate cells below)
Date:
Plan:
Do:
Study:
Act:
Intervention: PDSA Cycle #3 (Please enter information in the appropriate cells below)
Date:
Plan:
Do:
Study:
Act:
Note on A12: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A13: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A14: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A15: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A18: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A19: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A20: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A21: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A24: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A25: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A26: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A27: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A30: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A31: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A32: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A33: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A36: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A37: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A38: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A39: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A42: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A43: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A44: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A45: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A48: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A49: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A50: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A51: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A54: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A55: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A56: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A57: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A60: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A61: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A62: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A63: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A66: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A67: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A68: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A69: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A72: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A73: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A74: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A75: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A78: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A79: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A80: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
Note on A81: What barriers do you anticipate and what strategies will you use to address them? What stakeholder groups (clinical professionals, community based organizations, government departments) need to be involved in this activity? What Technical Assistance (TA) do you need to be able to move forward? Have any issues arisen with enrollment into or engagement of patients in the intervention? Have any details of the intervention strategy changed since the last reporting period?
P D A S

## Pilot Data Report
PILOT MEASURES | [7 empty] | Yes
Title: |  | Project Title here
Organization Name: |  | On Schedule of Reporting tab, enter Organization/Plan/Practice Name
Contact Name: |  | On Schedule of Reporting tab, enter contact person's name
Contact Phone Number: |  | On Schedule of Reporting tab, enter phone number (with area code)
Submission Date: |  | On Schedule of Reporting tab, enter date (DD/MM/YY)
Identification measure #1 | Enter the name of the measure on the Pilot Planning Tool Tab
Description of measure
Population
Numerator | Enter this descriptive information on the Pilot Planning Tool Tab
Denominator | Enter this descriptive information on the Pilot Planning Tool Tab
Are the data in the numerator cumlative over time (yes/no)? |  |  |  | Are the data in the denominator cumlative over time (yes/no)?
Data Source
Notes regarding the data for this measure:
Pilot population |  |  |  | Comparison population (IF APPLICABLE)
Report Date | Numerator (number) | Denominator (number) | Rate or results | Report Date | Numerator (number | Denominator (number) | Rate or results
2006-04-15 |  |  | #DIV/0! | 2006-04-15 |  |  | #DIV/0!
2006-06-15 |  |  | #DIV/0! | 2006-06-15 |  |  | #DIV/0!
2006-08-15 |  |  | #DIV/0! | 2006-08-15 |  |  | #DIV/0!
2006-10-15 |  |  | #DIV/0! | 2006-10-15 |  |  | #DIV/0!
2006-12-15 |  |  | #DIV/0! | 2006-12-15 |  |  | #DIV/0!
2007-03-15 |  |  | #DIV/0! | 2007-03-15 |  |  | #DIV/0!
2007-06-15 |  |  | #DIV/0! | 2007-06-15 |  |  | #DIV/0!
2007-09-15 |  |  | #DIV/0! | 2007-09-15 |  |  | #DIV/0!
2007-12-15 |  |  | #DIV/0! | 2007-12-15 |  |  | #DIV/0!
2008-03-15 |  |  | #DIV/0! | 2008-03-15 |  |  | #DIV/0!
2008-06-15 |  |  | #DIV/0! | 2008-06-15 |  |  | #DIV/0!
2008-09-15 |  |  | #DIV/0! | 2008-09-15 |  |  | #DIV/0!
2008-12-15 |  |  | #DIV/0! | 2008-12-15 |  |  | #DIV/0!
2009-03-15 |  |  | #DIV/0! | 2009-03-15 |  |  | #DIV/0!
2009-06-15 |  |  | #DIV/0! | 2009-06-15 |  |  | #DIV/0!
2009-09-15 |  |  | #DIV/0! | 2009-09-15 |  |  | #DIV/0!
2009-12-15 |  |  | #DIV/0! | 2009-12-15 |  |  | #DIV/0!
2010-03-15 |  |  | #DIV/0! | 2010-03-15 |  |  | #DIV/0!
2010-06-15 |  |  | #DIV/0! | 2010-06-15 |  |  | #DIV/0!
2010-09-15 |  |  | #DIV/0! | 2010-09-15 |  |  | #DIV/0!
2010-12-15 |  |  | #DIV/0! | 2010-12-15 |  |  | #DIV/0!
2011-03-15 |  |  | #DIV/0! | 2011-03-15 |  |  | #DIV/0!
2011-06-15 |  |  | #DIV/0! | 2011-06-15 |  |  | #DIV/0!
2011-09-15 |  |  | #DIV/0! | 2011-09-15 |  |  | #DIV/0!
Identification measure #2 | Enter the name of the measure on the Pilot Planning Tool Tab
Description of measure
Population
Numerator | Enter this descriptive information on the Pilot Planning Tool Tab
Denominator | Enter this descriptive information on the Pilot Planning Tool Tab
Are the data in the numerator cumlative over time (yes/no)? |  |  |  | Are the data in the denominator cumlative over time (yes/no)?
Data Source
Notes regarding the data for this measure:
Pilot population |  |  |  | Comparison population (IF APPLICABLE)
Report Date | Numerator (number) | Denominator (number) | Rate or results | Report Date | Numerator (number | Denominator (number) | Rate or results
2006-04-15 |  |  | #DIV/0! | 2006-04-15 |  |  | #DIV/0!
2006-06-15 |  |  | #DIV/0! | 2006-06-15 |  |  | #DIV/0!
2006-08-15 |  |  | #DIV/0! | 2006-08-15 |  |  | #DIV/0!
2006-10-15 |  |  | #DIV/0! | 2006-10-15 |  |  | #DIV/0!
2006-12-15 |  |  | #DIV/0! | 2006-12-15 |  |  | #DIV/0!
2007-03-15 |  |  | #DIV/0! | 2007-03-15 |  |  | #DIV/0!
2007-06-15 |  |  | #DIV/0! | 2007-06-15 |  |  | #DIV/0!
2007-09-15 |  |  | #DIV/0! | 2007-09-15 |  |  | #DIV/0!
2007-12-15 |  |  | #DIV/0! | 2007-12-15 |  |  | #DIV/0!
2008-03-15 |  |  | #DIV/0! | 2008-03-15 |  |  | #DIV/0!
2008-06-15 |  |  | #DIV/0! | 2008-06-15 |  |  | #DIV/0!
2008-09-15 |  |  | #DIV/0! | 2008-09-15 |  |  | #DIV/0!
2008-12-15 |  |  | #DIV/0! | 2008-12-15 |  |  | #DIV/0!
2009-03-15 |  |  | #DIV/0! | 2009-03-15 |  |  | #DIV/0!
2009-06-15 |  |  | #DIV/0! | 2009-06-15 |  |  | #DIV/0!
2009-09-15 |  |  | #DIV/0! | 2009-09-15 |  |  | #DIV/0!
2009-12-15 |  |  | #DIV/0! | 2009-12-15 |  |  | #DIV/0!
2010-03-15 |  |  | #DIV/0! | 2010-03-15 |  |  | #DIV/0!
2010-06-15 |  |  | #DIV/0! | 2010-06-15 |  |  | #DIV/0!
2010-09-15 |  |  | #DIV/0! | 2010-09-15 |  |  | #DIV/0!
2010-12-15 |  |  | #DIV/0! | 2010-12-15 |  |  | #DIV/0!
2011-03-15 |  |  | #DIV/0! | 2011-03-15 |  |  | #DIV/0!
2011-06-15 |  |  | #DIV/0! | 2011-06-15 |  |  | #DIV/0!
2011-09-15 |  |  | #DIV/0! | 2011-09-15 |  |  | #DIV/0!
Stratification Measure #1 | Enter the name of the measure on the Pilot Planning Tool Tab
Description of measure
Population
Numerator | Enter this descriptive information on the Pilot Planning Tool Tab
Denominator | Enter this descriptive information on the Pilot Planning Tool Tab
Are the data in the numerator cumlative over time (yes/no)? |  |  |  | Are the data in the denominator cumlative over time (yes/no)?
Data Source
Notes regarding the data for this measure:
Pilot population |  |  |  | Comparison population (IF APPLICABLE)
Report Date | Numerator (number) | Denominator (number) | Rate or results | Report Date | Numerator (number | Denominator (number) | Rate or results
2006-04-15 |  |  | #DIV/0! | 2006-04-15 |  |  | #DIV/0!
2006-06-15 |  |  | #DIV/0! | 2006-06-15 |  |  | #DIV/0!
2006-08-15 |  |  | #DIV/0! | 2006-08-15 |  |  | #DIV/0!
2006-10-15 |  |  | #DIV/0! | 2006-10-15 |  |  | #DIV/0!
2006-12-15 |  |  | #DIV/0! | 2006-12-15 |  |  | #DIV/0!
2007-03-15 |  |  | #DIV/0! | 2007-03-15 |  |  | #DIV/0!
2007-06-15 |  |  | #DIV/0! | 2007-06-15 |  |  | #DIV/0!
2007-09-15 |  |  | #DIV/0! | 2007-09-15 |  |  | #DIV/0!
2007-12-15 |  |  | #DIV/0! | 2007-12-15 |  |  | #DIV/0!
2008-03-15 |  |  | #DIV/0! | 2008-03-15 |  |  | #DIV/0!
2008-06-15 |  |  | #DIV/0! | 2008-06-15 |  |  | #DIV/0!
2008-09-15 |  |  | #DIV/0! | 2008-09-15 |  |  | #DIV/0!
2008-12-15 |  |  | #DIV/0! | 2008-12-15 |  |  | #DIV/0!
2009-03-15 |  |  | #DIV/0! | 2009-03-15 |  |  | #DIV/0!
2009-06-15 |  |  | #DIV/0! | 2009-06-15 |  |  | #DIV/0!
2009-09-15 |  |  | #DIV/0! | 2009-09-15 |  |  | #DIV/0!
2009-12-15 |  |  | #DIV/0! | 2009-12-15 |  |  | #DIV/0!
2010-03-15 |  |  | #DIV/0! | 2010-03-15 |  |  | #DIV/0!
2010-06-15 |  |  | #DIV/0! | 2010-06-15 |  |  | #DIV/0!
2010-09-15 |  |  | #DIV/0! | 2010-09-15 |  |  | #DIV/0!
2010-12-15 |  |  | #DIV/0! | 2010-12-15 |  |  | #DIV/0!
2011-03-15 |  |  | #DIV/0! | 2011-03-15 |  |  | #DIV/0!
2011-06-15 |  |  | #DIV/0! | 2011-06-15 |  |  | #DIV/0!
2011-09-15 |  |  | #DIV/0! | 2011-09-15 |  |  | #DIV/0!
Stratification Measure #2 | Enter the name of the measure on the Pilot Planning Tool Tab
Description of measure
Population
Numerator | Enter this descriptive information on the Pilot Planning Tool Tab
Denominator | Enter this descriptive information on the Pilot Planning Tool Tab
Are the data in the numerator cumlative over time (yes/no)? |  |  |  | Are the data in the denominator cumlative over time (yes/no)?
Data Source
Notes regarding the data for this measure:
Pilot population |  |  |  | Comparison population (IF APPLICABLE)
Report Date | Numerator (number) | Denominator (number) | Rate or results | Report Date | Numerator (number | Denominator (number) | Rate or results
2006-04-15 |  |  | #DIV/0! | 2006-04-15 |  |  | #DIV/0!
2006-06-15 |  |  | #DIV/0! | 2006-06-15 |  |  | #DIV/0!
2006-08-15 |  |  | #DIV/0! | 2006-08-15 |  |  | #DIV/0!
2006-10-15 |  |  | #DIV/0! | 2006-10-15 |  |  | #DIV/0!
2006-12-15 |  |  | #DIV/0! | 2006-12-15 |  |  | #DIV/0!
2007-03-15 |  |  | #DIV/0! | 2007-03-15 |  |  | #DIV/0!
2007-06-15 |  |  | #DIV/0! | 2007-06-15 |  |  | #DIV/0!
2007-09-15 |  |  | #DIV/0! | 2007-09-15 |  |  | #DIV/0!
2007-12-15 |  |  | #DIV/0! | 2007-12-15 |  |  | #DIV/0!
2008-03-15 |  |  | #DIV/0! | 2008-03-15 |  |  | #DIV/0!
2008-06-15 |  |  | #DIV/0! | 2008-06-15 |  |  | #DIV/0!
2008-09-15 |  |  | #DIV/0! | 2008-09-15 |  |  | #DIV/0!
2008-12-15 |  |  | #DIV/0! | 2008-12-15 |  |  | #DIV/0!
2009-03-15 |  |  | #DIV/0! | 2009-03-15 |  |  | #DIV/0!
2009-06-15 |  |  | #DIV/0! | 2009-06-15 |  |  | #DIV/0!
2009-09-15 |  |  | #DIV/0! | 2009-09-15 |  |  | #DIV/0!
2009-12-15 |  |  | #DIV/0! | 2009-12-15 |  |  | #DIV/0!
2010-03-15 |  |  | #DIV/0! | 2010-03-15 |  |  | #DIV/0!
2010-06-15 |  |  | #DIV/0! | 2010-06-15 |  |  | #DIV/0!
2010-09-15 |  |  | #DIV/0! | 2010-09-15 |  |  | #DIV/0!
2010-12-15 |  |  | #DIV/0! | 2010-12-15 |  |  | #DIV/0!
2011-03-15 |  |  | #DIV/0! | 2011-03-15 |  |  | #DIV/0!
2011-06-15 |  |  | #DIV/0! | 2011-06-15 |  |  | #DIV/0!
2011-09-15 |  |  | #DIV/0! | 2011-09-15 |  |  | #DIV/0!
Stratification Measure #3 | Enter the name of the measure on the Pilot Planning Tool Tab
Description of measure
Population
Numerator | Enter this descriptive information on the Pilot Planning Tool Tab
Denominator | Enter this descriptive information on the Pilot Planning Tool Tab
Are the data in the numerator cumlative over time (yes/no)? |  |  |  | Are the data in the denominator cumlative over time (yes/no)?
Data Source
Notes regarding the data for this measure:
Pilot population |  |  |  | Comparison population (IF APPLICABLE)
Report Date | Numerator (number) | Denominator (number) | Rate or results | Report Date | Numerator (number | Denominator (number) | Rate or results
2006-04-15 |  |  | #DIV/0! | 2006-04-15 |  |  | #DIV/0!
2006-06-15 |  |  | #DIV/0! | 2006-06-15 |  |  | #DIV/0!
2006-08-15 |  |  | #DIV/0! | 2006-08-15 |  |  | #DIV/0!
2006-10-15 |  |  | #DIV/0! | 2006-10-15 |  |  | #DIV/0!
2006-12-15 |  |  | #DIV/0! | 2006-12-15 |  |  | #DIV/0!
2007-03-15 |  |  | #DIV/0! | 2007-03-15 |  |  | #DIV/0!
2007-06-15 |  |  | #DIV/0! | 2007-06-15 |  |  | #DIV/0!
2007-09-15 |  |  | #DIV/0! | 2007-09-15 |  |  | #DIV/0!
2007-12-15 |  |  | #DIV/0! | 2007-12-15 |  |  | #DIV/0!
2008-03-15 |  |  | #DIV/0! | 2008-03-15 |  |  | #DIV/0!
2008-06-15 |  |  | #DIV/0! | 2008-06-15 |  |  | #DIV/0!
2008-09-15 |  |  | #DIV/0! | 2008-09-15 |  |  | #DIV/0!
2008-12-15 |  |  | #DIV/0! | 2008-12-15 |  |  | #DIV/0!
2009-03-15 |  |  | #DIV/0! | 2009-03-15 |  |  | #DIV/0!
2009-06-15 |  |  | #DIV/0! | 2009-06-15 |  |  | #DIV/0!
2009-09-15 |  |  | #DIV/0! | 2009-09-15 |  |  | #DIV/0!
2009-12-15 |  |  | #DIV/0! | 2009-12-15 |  |  | #DIV/0!
2010-03-15 |  |  | #DIV/0! | 2010-03-15 |  |  | #DIV/0!
2010-06-15 |  |  | #DIV/0! | 2010-06-15 |  |  | #DIV/0!
2010-09-15 |  |  | #DIV/0! | 2010-09-15 |  |  | #DIV/0!
2010-12-15 |  |  | #DIV/0! | 2010-12-15 |  |  | #DIV/0!
2011-03-15 |  |  | #DIV/0! | 2011-03-15 |  |  | #DIV/0!
2011-06-15 |  |  | #DIV/0! | 2011-06-15 |  |  | #DIV/0!
2011-09-15 |  |  | #DIV/0! | 2011-09-15 |  |  | #DIV/0!
Outreach Measure #1 | Enter the name of the measure on the Pilot Planning Tool Tab
Description of measure
Population
Numerator | Enter this descriptive information on the Pilot Planning Tool Tab
Denominator | Enter this descriptive information on the Pilot Planning Tool Tab
Are the data in the numerator cumlative over time (yes/no)? |  |  |  | Are the data in the denominator cumlative over time (yes/no)?
Data Source
Notes regarding the data for this measure:
Pilot population |  |  |  | Comparison population (IF APPLICABLE)
Report Date | Numerator (number) | Denominator (number) | Rate or results | Report Date | Numerator (number | Denominator (number) | Rate or results
2006-04-15 |  |  | #DIV/0! | 2006-04-15 |  |  | #DIV/0!
2006-06-15 |  |  | #DIV/0! | 2006-06-15 |  |  | #DIV/0!
2006-08-15 |  |  | #DIV/0! | 2006-08-15 |  |  | #DIV/0!
2006-10-15 |  |  | #DIV/0! | 2006-10-15 |  |  | #DIV/0!
2006-12-15 |  |  | #DIV/0! | 2006-12-15 |  |  | #DIV/0!
2007-03-15 |  |  | #DIV/0! | 2007-03-15 |  |  | #DIV/0!
2007-06-15 |  |  | #DIV/0! | 2007-06-15 |  |  | #DIV/0!
2007-09-15 |  |  | #DIV/0! | 2007-09-15 |  |  | #DIV/0!
2007-12-15 |  |  | #DIV/0! | 2007-12-15 |  |  | #DIV/0!
2008-03-15 |  |  | #DIV/0! | 2008-03-15 |  |  | #DIV/0!
2008-06-15 |  |  | #DIV/0! | 2008-06-15 |  |  | #DIV/0!
2008-09-15 |  |  | #DIV/0! | 2008-09-15 |  |  | #DIV/0!
2008-12-15 |  |  | #DIV/0! | 2008-12-15 |  |  | #DIV/0!
2009-03-15 |  |  | #DIV/0! | 2009-03-15 |  |  | #DIV/0!
2009-06-15 |  |  | #DIV/0! | 2009-06-15 |  |  | #DIV/0!
2009-09-15 |  |  | #DIV/0! | 2009-09-15 |  |  | #DIV/0!
2009-12-15 |  |  | #DIV/0! | 2009-12-15 |  |  | #DIV/0!
2010-03-15 |  |  | #DIV/0! | 2010-03-15 |  |  | #DIV/0!
2010-06-15 |  |  | #DIV/0! | 2010-06-15 |  |  | #DIV/0!
2010-09-15 |  |  | #DIV/0! | 2010-09-15 |  |  | #DIV/0!
2010-12-15 |  |  | #DIV/0! | 2010-12-15 |  |  | #DIV/0!
2011-03-15 |  |  | #DIV/0! | 2011-03-15 |  |  | #DIV/0!
2011-06-15 |  |  | #DIV/0! | 2011-06-15 |  |  | #DIV/0!
2011-09-15 |  |  | #DIV/0! | 2011-09-15 |  |  | #DIV/0!
Outreach Measure #2 | Enter the name of the measure on the Pilot Planning Tool Tab
Description of measure
Population
Numerator | Enter this descriptive information on the Pilot Planning Tool Tab
Denominator | Enter this descriptive information on the Pilot Planning Tool Tab
Are the data in the numerator cumlative over time (yes/no)? |  |  |  | Are the data in the denominator cumlative over time (yes/no)?
Data Source
Notes regarding the data for this measure:
Pilot population |  |  |  | Comparison population (IF APPLICABLE)
Report Date | Numerator (number) | Denominator (number) | Rate or results | Report Date | Numerator (number | Denominator (number) | Rate or results
2006-04-15 |  |  | #DIV/0! | 2006-04-15 |  |  | #DIV/0!
2006-06-15 |  |  | #DIV/0! | 2006-06-15 |  |  | #DIV/0!
2006-08-15 |  |  | #DIV/0! | 2006-08-15 |  |  | #DIV/0!
2006-10-15 |  |  | #DIV/0! | 2006-10-15 |  |  | #DIV/0!
2006-12-15 |  |  | #DIV/0! | 2006-12-15 |  |  | #DIV/0!
2007-03-15 |  |  | #DIV/0! | 2007-03-15 |  |  | #DIV/0!
2007-06-15 |  |  | #DIV/0! | 2007-06-15 |  |  | #DIV/0!
2007-09-15 |  |  | #DIV/0! | 2007-09-15 |  |  | #DIV/0!
2007-12-15 |  |  | #DIV/0! | 2007-12-15 |  |  | #DIV/0!
2008-03-15 |  |  | #DIV/0! | 2008-03-15 |  |  | #DIV/0!
2008-06-15 |  |  | #DIV/0! | 2008-06-15 |  |  | #DIV/0!
2008-09-15 |  |  | #DIV/0! | 2008-09-15 |  |  | #DIV/0!
2008-12-15 |  |  | #DIV/0! | 2008-12-15 |  |  | #DIV/0!
2009-03-15 |  |  | #DIV/0! | 2009-03-15 |  |  | #DIV/0!
2009-06-15 |  |  | #DIV/0! | 2009-06-15 |  |  | #DIV/0!
2009-09-15 |  |  | #DIV/0! | 2009-09-15 |  |  | #DIV/0!
2009-12-15 |  |  | #DIV/0! | 2009-12-15 |  |  | #DIV/0!
2010-03-15 |  |  | #DIV/0! | 2010-03-15 |  |  | #DIV/0!
2010-06-15 |  |  | #DIV/0! | 2010-06-15 |  |  | #DIV/0!
2010-09-15 |  |  | #DIV/0! | 2010-09-15 |  |  | #DIV/0!
2010-12-15 |  |  | #DIV/0! | 2010-12-15 |  |  | #DIV/0!
2011-03-15 |  |  | #DIV/0! | 2011-03-15 |  |  | #DIV/0!
2011-06-15 |  |  | #DIV/0! | 2011-06-15 |  |  | #DIV/0!
2011-09-15 |  |  | #DIV/0! | 2011-09-15 |  |  | #DIV/0!
Outreach Measure #3 | Enter the name of the measure on the Pilot Planning Tool Tab
Description of measure
Population
Numerator | Enter this descriptive information on the Pilot Planning Tool Tab
Denominator | Enter this descriptive information on the Pilot Planning Tool Tab
Are the data in the numerator cumlative over time (yes/no)? |  |  |  | Are the data in the denominator cumlative over time (yes/no)?
Data Source
Notes regarding the data for this measure:
Pilot population |  |  |  | Comparison population (IF APPLICABLE)
Report Date | Numerator (number) | Denominator (number) | Rate or results | Report Date | Numerator (number | Denominator (number) | Rate or results
2006-04-15 |  |  | #DIV/0! | 2006-04-15 |  |  | #DIV/0!
2006-06-15 |  |  | #DIV/0! | 2006-06-15 |  |  | #DIV/0!
2006-08-15 |  |  | #DIV/0! | 2006-08-15 |  |  | #DIV/0!
2006-10-15 |  |  | #DIV/0! | 2006-10-15 |  |  | #DIV/0!
2006-12-15 |  |  | #DIV/0! | 2006-12-15 |  |  | #DIV/0!
2007-03-15 |  |  | #DIV/0! | 2007-03-15 |  |  | #DIV/0!
2007-06-15 |  |  | #DIV/0! | 2007-06-15 |  |  | #DIV/0!
2007-09-15 |  |  | #DIV/0! | 2007-09-15 |  |  | #DIV/0!
2007-12-15 |  |  | #DIV/0! | 2007-12-15 |  |  | #DIV/0!
2008-03-15 |  |  | #DIV/0! | 2008-03-15 |  |  | #DIV/0!
2008-06-15 |  |  | #DIV/0! | 2008-06-15 |  |  | #DIV/0!
2008-09-15 |  |  | #DIV/0! | 2008-09-15 |  |  | #DIV/0!
2008-12-15 |  |  | #DIV/0! | 2008-12-15 |  |  | #DIV/0!
2009-03-15 |  |  | #DIV/0! | 2009-03-15 |  |  | #DIV/0!
2009-06-15 |  |  | #DIV/0! | 2009-06-15 |  |  | #DIV/0!
2009-09-15 |  |  | #DIV/0! | 2009-09-15 |  |  | #DIV/0!
2009-12-15 |  |  | #DIV/0! | 2009-12-15 |  |  | #DIV/0!
2010-03-15 |  |  | #DIV/0! | 2010-03-15 |  |  | #DIV/0!
2010-06-15 |  |  | #DIV/0! | 2010-06-15 |  |  | #DIV/0!
2010-09-15 |  |  | #DIV/0! | 2010-09-15 |  |  | #DIV/0!
2010-12-15 |  |  | #DIV/0! | 2010-12-15 |  |  | #DIV/0!
2011-03-15 |  |  | #DIV/0! | 2011-03-15 |  |  | #DIV/0!
2011-06-15 |  |  | #DIV/0! | 2011-06-15 |  |  | #DIV/0!
2011-09-15 |  |  | #DIV/0! | 2011-09-15 |  |  | #DIV/0!
Intervention Measure #1 | Enter the name of the measure on the Pilot Planning Tool Tab
Description of measure
Population
Numerator | Enter this descriptive information on the Pilot Planning Tool Tab
Denominator | Enter this descriptive information on the Pilot Planning Tool Tab
Are the data in the numerator cumlative over time (yes/no)? |  |  |  | Are the data in the denominator cumlative over time (yes/no)?
Data Source
Notes regarding the data for this measure:
Pilot population |  |  |  | Comparison population (IF APPLICABLE)
Report Date | Numerator (number) | Denominator (number) | Rate or results | Report Date | Numerator (number | Denominator (number) | Rate or results
2006-04-15 |  |  | #DIV/0! | 2006-04-15 |  |  | #DIV/0!
2006-06-15 |  |  | #DIV/0! | 2006-06-15 |  |  | #DIV/0!
2006-08-15 |  |  | #DIV/0! | 2006-08-15 |  |  | #DIV/0!
2006-10-15 |  |  | #DIV/0! | 2006-10-15 |  |  | #DIV/0!
2006-12-15 |  |  | #DIV/0! | 2006-12-15 |  |  | #DIV/0!
2007-03-15 |  |  | #DIV/0! | 2007-03-15 |  |  | #DIV/0!
2007-06-15 |  |  | #DIV/0! | 2007-06-15 |  |  | #DIV/0!
2007-09-15 |  |  | #DIV/0! | 2007-09-15 |  |  | #DIV/0!
2007-12-15 |  |  | #DIV/0! | 2007-12-15 |  |  | #DIV/0!
2008-03-15 |  |  | #DIV/0! | 2008-03-15 |  |  | #DIV/0!
2008-06-15 |  |  | #DIV/0! | 2008-06-15 |  |  | #DIV/0!
2008-09-15 |  |  | #DIV/0! | 2008-09-15 |  |  | #DIV/0!
2008-12-15 |  |  | #DIV/0! | 2008-12-15 |  |  | #DIV/0!
2009-03-15 |  |  | #DIV/0! | 2009-03-15 |  |  | #DIV/0!
2009-06-15 |  |  | #DIV/0! | 2009-06-15 |  |  | #DIV/0!
2009-09-15 |  |  | #DIV/0! | 2009-09-15 |  |  | #DIV/0!
2009-12-15 |  |  | #DIV/0! | 2009-12-15 |  |  | #DIV/0!
2010-03-15 |  |  | #DIV/0! | 2010-03-15 |  |  | #DIV/0!
2010-06-15 |  |  | #DIV/0! | 2010-06-15 |  |  | #DIV/0!
2010-09-15 |  |  | #DIV/0! | 2010-09-15 |  |  | #DIV/0!
2010-12-15 |  |  | #DIV/0! | 2010-12-15 |  |  | #DIV/0!
2011-03-15 |  |  | #DIV/0! | 2011-03-15 |  |  | #DIV/0!
2011-06-15 |  |  | #DIV/0! | 2011-06-15 |  |  | #DIV/0!
2011-09-15 |  |  | #DIV/0! | 2011-09-15 |  |  | #DIV/0!
Intervention Measure #2 | Enter the name of the measure on the Pilot Planning Tool Tab
Description of measure
Population
Numerator | Enter this descriptive information on the Pilot Planning Tool Tab
Denominator | Enter this descriptive information on the Pilot Planning Tool Tab
Are the data in the numerator cumlative over time (yes/no)? |  |  |  | Are the data in the denominator cumlative over time (yes/no)?
Data Source
Notes regarding the data for this measure:
Pilot population |  |  |  | Comparison population (IF APPLICABLE)
Report Date | Numerator (number) | Denominator (number) | Rate or results | Report Date | Numerator (number | Denominator (number) | Rate or results
2006-04-15 |  |  | #DIV/0! | 2006-04-15 |  |  | #DIV/0!
2006-06-15 |  |  | #DIV/0! | 2006-06-15 |  |  | #DIV/0!
2006-08-15 |  |  | #DIV/0! | 2006-08-15 |  |  | #DIV/0!
2006-10-15 |  |  | #DIV/0! | 2006-10-15 |  |  | #DIV/0!
2006-12-15 |  |  | #DIV/0! | 2006-12-15 |  |  | #DIV/0!
2007-03-15 |  |  | #DIV/0! | 2007-03-15 |  |  | #DIV/0!
2007-06-15 |  |  | #DIV/0! | 2007-06-15 |  |  | #DIV/0!
2007-09-15 |  |  | #DIV/0! | 2007-09-15 |  |  | #DIV/0!
2007-12-15 |  |  | #DIV/0! | 2007-12-15 |  |  | #DIV/0!
2008-03-15 |  |  | #DIV/0! | 2008-03-15 |  |  | #DIV/0!
2008-06-15 |  |  | #DIV/0! | 2008-06-15 |  |  | #DIV/0!
2008-09-15 |  |  | #DIV/0! | 2008-09-15 |  |  | #DIV/0!
2008-12-15 |  |  | #DIV/0! | 2008-12-15 |  |  | #DIV/0!
2009-03-15 |  |  | #DIV/0! | 2009-03-15 |  |  | #DIV/0!
2009-06-15 |  |  | #DIV/0! | 2009-06-15 |  |  | #DIV/0!
2009-09-15 |  |  | #DIV/0! | 2009-09-15 |  |  | #DIV/0!
2009-12-15 |  |  | #DIV/0! | 2009-12-15 |  |  | #DIV/0!
2010-03-15 |  |  | #DIV/0! | 2010-03-15 |  |  | #DIV/0!
2010-06-15 |  |  | #DIV/0! | 2010-06-15 |  |  | #DIV/0!
2010-09-15 |  |  | #DIV/0! | 2010-09-15 |  |  | #DIV/0!
2010-12-15 |  |  | #DIV/0! | 2010-12-15 |  |  | #DIV/0!
2011-03-15 |  |  | #DIV/0! | 2011-03-15 |  |  | #DIV/0!
2011-06-15 |  |  | #DIV/0! | 2011-06-15 |  |  | #DIV/0!
2011-09-15 |  |  | #DIV/0! | 2011-09-15 |  |  | #DIV/0!
Intervention Measure #3 | Enter the name of the measure on the Pilot Planning Tool Tab
Description of measure
Population
Numerator | Enter this descriptive information on the Pilot Planning Tool Tab
Denominator | Enter this descriptive information on the Pilot Planning Tool Tab
Are the data in the numerator cumlative over time (yes/no)? |  |  |  | Are the data in the denominator cumlative over time (yes/no)?
Data Source
Notes regarding the data for this measure:
Pilot population |  |  |  | Comparison population (IF APPLICABLE)
Report Date | Numerator (number) | Denominator (number) | Rate or results | Report Date | Numerator (number | Denominator (number) | Rate or results
2006-04-15 |  |  | #DIV/0! | 2006-04-15 |  |  | #DIV/0!
2006-06-15 |  |  | #DIV/0! | 2006-06-15 |  |  | #DIV/0!
2006-08-15 |  |  | #DIV/0! | 2006-08-15 |  |  | #DIV/0!
2006-10-15 |  |  | #DIV/0! | 2006-10-15 |  |  | #DIV/0!
2006-12-15 |  |  | #DIV/0! | 2006-12-15 |  |  | #DIV/0!
2007-03-15 |  |  | #DIV/0! | 2007-03-15 |  |  | #DIV/0!
2007-06-15 |  |  | #DIV/0! | 2007-06-15 |  |  | #DIV/0!
2007-09-15 |  |  | #DIV/0! | 2007-09-15 |  |  | #DIV/0!
2007-12-15 |  |  | #DIV/0! | 2007-12-15 |  |  | #DIV/0!
2008-03-15 |  |  | #DIV/0! | 2008-03-15 |  |  | #DIV/0!
2008-06-15 |  |  | #DIV/0! | 2008-06-15 |  |  | #DIV/0!
2008-09-15 |  |  | #DIV/0! | 2008-09-15 |  |  | #DIV/0!
2008-12-15 |  |  | #DIV/0! | 2008-12-15 |  |  | #DIV/0!
2009-03-15 |  |  | #DIV/0! | 2009-03-15 |  |  | #DIV/0!
2009-06-15 |  |  | #DIV/0! | 2009-06-15 |  |  | #DIV/0!
2009-09-15 |  |  | #DIV/0! | 2009-09-15 |  |  | #DIV/0!
2009-12-15 |  |  | #DIV/0! | 2009-12-15 |  |  | #DIV/0!
2010-03-15 |  |  | #DIV/0! | 2010-03-15 |  |  | #DIV/0!
2010-06-15 |  |  | #DIV/0! | 2010-06-15 |  |  | #DIV/0!
2010-09-15 |  |  | #DIV/0! | 2010-09-15 |  |  | #DIV/0!
2010-12-15 |  |  | #DIV/0! | 2010-12-15 |  |  | #DIV/0!
2011-03-15 |  |  | #DIV/0! | 2011-03-15 |  |  | #DIV/0!
2011-06-15 |  |  | #DIV/0! | 2011-06-15 |  |  | #DIV/0!
2011-09-15 |  |  | #DIV/0! | 2011-09-15 |  |  | #DIV/0!
Overall Aim Measure #1 | Enter the name of the measure on the Pilot Planning Tool Tab
Description of measure | Enter this descriptive information on the Pilot Planning Tool Tab
Population | Enter this descriptive information on the Pilot Planning Tool Tab
Numerator | Enter this descriptive information on the Pilot Planning Tool Tab
Denominator | Enter this descriptive information on the Pilot Planning Tool Tab
Are the data in the numerator cumlative over time (yes/no)? |  |  |  | Are the data in the denominator cumlative over time (yes/no)?
Data Source
Notes regarding the data for this measure:
Pilot population |  |  |  | Comparison population (IF APPLICABLE)
Report Date | Numerator (number) | Denominator (number) | Rate or results | Report Date | Numerator (number | Denominator (number) | Rate or results
2006-04-15 |  |  | #DIV/0! | 2006-04-15 |  |  | #DIV/0!
2006-06-15 |  |  | #DIV/0! | 2006-06-15 |  |  | #DIV/0!
2006-08-15 |  |  | #DIV/0! | 2006-08-15 |  |  | #DIV/0!
2006-10-15 |  |  | #DIV/0! | 2006-10-15 |  |  | #DIV/0!
2006-12-15 |  |  | #DIV/0! | 2006-12-15 |  |  | #DIV/0!
2007-03-15 |  |  | #DIV/0! | 2007-03-15 |  |  | #DIV/0!
2007-06-15 |  |  | #DIV/0! | 2007-06-15 |  |  | #DIV/0!
2007-09-15 |  |  | #DIV/0! | 2007-09-15 |  |  | #DIV/0!
2007-12-15 |  |  | #DIV/0! | 2007-12-15 |  |  | #DIV/0!
2008-03-15 |  |  | #DIV/0! | 2008-03-15 |  |  | #DIV/0!
2008-06-15 |  |  | #DIV/0! | 2008-06-15 |  |  | #DIV/0!
2008-09-15 |  |  | #DIV/0! | 2008-09-15 |  |  | #DIV/0!
2008-12-15 |  |  | #DIV/0! | 2008-12-15 |  |  | #DIV/0!
2009-03-15 |  |  | #DIV/0! | 2009-03-15 |  |  | #DIV/0!
2009-06-15 |  |  | #DIV/0! | 2009-06-15 |  |  | #DIV/0!
2009-09-15 |  |  | #DIV/0! | 2009-09-15 |  |  | #DIV/0!
2009-12-15 |  |  | #DIV/0! | 2009-12-15 |  |  | #DIV/0!
2010-03-15 |  |  | #DIV/0! | 2010-03-15 |  |  | #DIV/0!
2010-06-15 |  |  | #DIV/0! | 2010-06-15 |  |  | #DIV/0!
2010-09-15 |  |  | #DIV/0! | 2010-09-15 |  |  | #DIV/0!
2010-12-15 |  |  | #DIV/0! | 2010-12-15 |  |  | #DIV/0!
2011-03-15 |  |  | #DIV/0! | 2011-03-15 |  |  | #DIV/0!
2011-06-15 |  |  | #DIV/0! | 2011-06-15 |  |  | #DIV/0!
2011-09-15 |  |  | #DIV/0! | 2011-09-15 |  |  | #DIV/0!
Overall Aim Measure #2 | Enter the name of the measure on the Pilot Planning Tool Tab
Description of measure | Enter this descriptive information on the Pilot Planning Tool Tab
Population | Enter this descriptive information on the Pilot Planning Tool Tab
Numerator | Enter this descriptive information on the Pilot Planning Tool Tab
Denominator | Enter this descriptive information on the Pilot Planning Tool Tab
Are the data in the numerator cumlative over time (yes/no)? |  |  |  | Are the data in the denominator cumlative over time (yes/no)?
Data Source
Notes regarding the data for this measure:
Pilot population |  |  |  | Comparison population (IF APPLICABLE)
Report Date | Numerator (number) | Denominator (number) | Rate or results | Report Date | Numerator (number | Denominator (number) | Rate or results
2006-04-15 |  |  | #DIV/0! | 2006-04-15 |  |  | #DIV/0!
2006-06-15 |  |  | #DIV/0! | 2006-06-15 |  |  | #DIV/0!
2006-08-15 |  |  | #DIV/0! | 2006-08-15 |  |  | #DIV/0!
2006-10-15 |  |  | #DIV/0! | 2006-10-15 |  |  | #DIV/0!
2006-12-15 |  |  | #DIV/0! | 2006-12-15 |  |  | #DIV/0!
2007-03-15 |  |  | #DIV/0! | 2007-03-15 |  |  | #DIV/0!
2007-06-15 |  |  | #DIV/0! | 2007-06-15 |  |  | #DIV/0!
2007-09-15 |  |  | #DIV/0! | 2007-09-15 |  |  | #DIV/0!
2007-12-15 |  |  | #DIV/0! | 2007-12-15 |  |  | #DIV/0!
2008-03-15 |  |  | #DIV/0! | 2008-03-15 |  |  | #DIV/0!
2008-06-15 |  |  | #DIV/0! | 2008-06-15 |  |  | #DIV/0!
2008-09-15 |  |  | #DIV/0! | 2008-09-15 |  |  | #DIV/0!
2008-12-15 |  |  | #DIV/0! | 2008-12-15 |  |  | #DIV/0!
2009-03-15 |  |  | #DIV/0! | 2009-03-15 |  |  | #DIV/0!
2009-06-15 |  |  | #DIV/0! | 2009-06-15 |  |  | #DIV/0!
2009-09-15 |  |  | #DIV/0! | 2009-09-15 |  |  | #DIV/0!
2009-12-15 |  |  | #DIV/0! | 2009-12-15 |  |  | #DIV/0!
2010-03-15 |  |  | #DIV/0! | 2010-03-15 |  |  | #DIV/0!
2010-06-15 |  |  | #DIV/0! | 2010-06-15 |  |  | #DIV/0!
2010-09-15 |  |  | #DIV/0! | 2010-09-15 |  |  | #DIV/0!
2010-12-15 |  |  | #DIV/0! | 2010-12-15 |  |  | #DIV/0!
2011-03-15 |  |  | #DIV/0! | 2011-03-15 |  |  | #DIV/0!
2011-06-15 |  |  | #DIV/0! | 2011-06-15 |  |  | #DIV/0!
2011-09-15 |  |  | #DIV/0! | 2011-09-15 |  |  | #DIV/0!
0
Overall Aim Measure #3 | Enter the name of the measure on the Pilot Planning Tool Tab
Description of measure | Enter this descriptive information on the Pilot Planning Tool Tab
Population | Enter this descriptive information on the Pilot Planning Tool Tab
Numerator | Enter this descriptive information on the Pilot Planning Tool Tab
Denominator | Enter this descriptive information on the Pilot Planning Tool Tab
Are the data in the numerator cumlative over time (yes/no)? |  |  |  | Are the data in the denominator cumlative over time (yes/no)?
Data Source
Notes regarding the data for this measure:
Pilot population |  |  |  | Comparison population (IF APPLICABLE)
Report Date | Numerator (number) | Denominator (number) | Rate or results | Report Date | Numerator (number | Denominator (number) | Rate or results
2006-04-15 |  |  | #DIV/0! | 2006-04-15 |  |  | #DIV/0!
2006-06-15 |  |  | #DIV/0! | 2006-06-15 |  |  | #DIV/0!
2006-08-15 |  |  | #DIV/0! | 2006-08-15 |  |  | #DIV/0!
2006-10-15 |  |  | #DIV/0! | 2006-10-15 |  |  | #DIV/0!
2006-12-15 |  |  | #DIV/0! | 2006-12-15 |  |  | #DIV/0!
2007-03-15 |  |  | #DIV/0! | 2007-03-15 |  |  | #DIV/0!
2007-06-15 |  |  | #DIV/0! | 2007-06-15 |  |  | #DIV/0!
2007-09-15 |  |  | #DIV/0! | 2007-09-15 |  |  | #DIV/0!
2007-12-15 |  |  | #DIV/0! | 2007-12-15 |  |  | #DIV/0!
2008-03-15 |  |  | #DIV/0! | 2008-03-15 |  |  | #DIV/0!
2008-06-15 |  |  | #DIV/0! | 2008-06-15 |  |  | #DIV/0!
2008-09-15 |  |  | #DIV/0! | 2008-09-15 |  |  | #DIV/0!
2008-12-15 |  |  | #DIV/0! | 2008-12-15 |  |  | #DIV/0!
2009-03-15 |  |  | #DIV/0! | 2009-03-15 |  |  | #DIV/0!
2009-06-15 |  |  | #DIV/0! | 2009-06-15 |  |  | #DIV/0!
2009-09-15 |  |  | #DIV/0! | 2009-09-15 |  |  | #DIV/0!
2009-12-15 |  |  | #DIV/0! | 2009-12-15 |  |  | #DIV/0!
2010-03-15 |  |  | #DIV/0! | 2010-03-15 |  |  | #DIV/0!
2010-06-15 |  |  | #DIV/0! | 2010-06-15 |  |  | #DIV/0!
2010-09-15 |  |  | #DIV/0! | 2010-09-15 |  |  | #DIV/0!
2010-12-15 |  |  | #DIV/0! | 2010-12-15 |  |  | #DIV/0!
2011-03-15 |  |  | #DIV/0! | 2011-03-15 |  |  | #DIV/0!
2011-06-15 |  |  | #DIV/0! | 2011-06-15 |  |  | #DIV/0!
2011-09-15 |  |  | #DIV/0! | 2011-09-15 |  |  | #DIV/0!
Overall Aim Measure #4 | Enter the name of the measure on the Pilot Planning Tool Tab
Description of measure | Enter this descriptive information on the Pilot Planning Tool Tab
Population | Enter this descriptive information on the Pilot Planning Tool Tab
Numerator | Enter this descriptive information on the Pilot Planning Tool Tab
Denominator | Enter this descriptive information on the Pilot Planning Tool Tab
Are the data in the numerator cumlative over time (yes/no)? |  |  |  | Are the data in the denominator cumlative over time (yes/no)?
Data Source
Notes regarding the data for this measure:
Pilot population |  |  |  | Comparison population (IF APPLICABLE)
Report Date | Numerator (number) | Denominator (number) | Rate or results | Report Date | Numerator (number | Denominator (number) | Rate or results
2006-04-15 |  |  | #DIV/0! | 2006-04-15 |  |  | #DIV/0!
2006-06-15 |  |  | #DIV/0! | 2006-06-15 |  |  | #DIV/0!
2006-08-15 |  |  | #DIV/0! | 2006-08-15 |  |  | #DIV/0!
2006-10-15 |  |  | #DIV/0! | 2006-10-15 |  |  | #DIV/0!
2006-12-15 |  |  | #DIV/0! | 2006-12-15 |  |  | #DIV/0!
2007-03-15 |  |  | #DIV/0! | 2007-03-15 |  |  | #DIV/0!
2007-06-15 |  |  | #DIV/0! | 2007-06-15 |  |  | #DIV/0!
2007-09-15 |  |  | #DIV/0! | 2007-09-15 |  |  | #DIV/0!
2007-12-15 |  |  | #DIV/0! | 2007-12-15 |  |  | #DIV/0!
2008-03-15 |  |  | #DIV/0! | 2008-03-15 |  |  | #DIV/0!
2008-06-15 |  |  | #DIV/0! | 2008-06-15 |  |  | #DIV/0!
2008-09-15 |  |  | #DIV/0! | 2008-09-15 |  |  | #DIV/0!
2008-12-15 |  |  | #DIV/0! | 2008-12-15 |  |  | #DIV/0!
2009-03-15 |  |  | #DIV/0! | 2009-03-15 |  |  | #DIV/0!
2009-06-15 |  |  | #DIV/0! | 2009-06-15 |  |  | #DIV/0!
2009-09-15 |  |  | #DIV/0! | 2009-09-15 |  |  | #DIV/0!
2009-12-15 |  |  | #DIV/0! | 2009-12-15 |  |  | #DIV/0!
2010-03-15 |  |  | #DIV/0! | 2010-03-15 |  |  | #DIV/0!
2010-06-15 |  |  | #DIV/0! | 2010-06-15 |  |  | #DIV/0!
2010-09-15 |  |  | #DIV/0! | 2010-09-15 |  |  | #DIV/0!
2010-12-15 |  |  | #DIV/0! | 2010-12-15 |  |  | #DIV/0!
2011-03-15 |  |  | #DIV/0! | 2011-03-15 |  |  | #DIV/0!
2011-06-15 |  |  | #DIV/0! | 2011-06-15 |  |  | #DIV/0!
2011-09-15 |  |  | #DIV/0! | 2011-09-15 |  |  | #DIV/0!
Note on A16: First report date is BASELINE data.
Note on A51: First report date is BASELINE data.
Note on A401: First report date is BASELINE data.
Note on A86: First report date is BASELINE data.
Note on A121: First report date is BASELINE data.
Note on A156: First report date is BASELINE data.
Note on A191: First report date is BASELINE data.
Note on A226: First report date is BASELINE data.
Note on A261: First report date is BASELINE data.
Note on A296: First report date is BASELINE data.
Note on A331: First report date is BASELINE data.
Note on A366: First report date is BASELINE data.
Note on A436: First report date is BASELINE data.
Note on A471: First report date is BASELINE data.
Note on A506: First report date is BASELINE data.
Note on E16: Please do not place your data in these cells if the Report Date cells are blank.
Note on E51: Please do not place your data in these cells if the Report Date cells are blank.
Note on E86: Please do not place your data in these cells if the Report Date cells are blank.
Note on E121: Please do not place your data in these cells if the Report Date cells are blank.
Note on E156: Please do not place your data in these cells if the Report Date cells are blank.
Note on E191: Please do not place your data in these cells if the Report Date cells are blank.
Note on E226: Please do not place your data in these cells if the Report Date cells are blank.
Note on E261: Please do not place your data in these cells if the Report Date cells are blank.
Note on E296: Please do not place your data in these cells if the Report Date cells are blank.
Note on E331: Please do not place your data in these cells if the Report Date cells are blank.
Note on E366: Please do not place your data in these cells if the Report Date cells are blank.
Note on E401: Please do not place your data in these cells if the Report Date cells are blank.
Note on E436: Please do not place your data in these cells if the Report Date cells are blank.
Note on E471: Please do not place your data in these cells if the Report Date cells are blank.
Note on E506: Please do not place your data in these cells if the Report Date cells are blank.

## Pilot Measure Graphs
Organization Name: | On Schedule of Reporting tab, enter Organization/Plan/Practice Name | Organization Name: | On Schedule of Reporting tab, enter Organization/Plan/Practice Name
Identification measure #1 | Enter the name of the measure on the Pilot Planning Tool Tab | Identification measure #2 | Enter the name of the measure on the Pilot Planning Tool Tab
Description of measure | 0 | Description of measure | 0
Population | 0 | Population | 0
Numerator | Enter this descriptive information on the Pilot Planning Tool Tab | Numerator | Enter this descriptive information on the Pilot Planning Tool Tab
Denominator | Enter this descriptive information on the Pilot Planning Tool Tab | Denominator | Enter this descriptive information on the Pilot Planning Tool Tab
Organization Name: | On Schedule of Reporting tab, enter Organization/Plan/Practice Name | Organization Name: | On Schedule of Reporting tab, enter Organization/Plan/Practice Name
Stratification Measure #1 | Enter the name of the measure on the Pilot Planning Tool Tab | Stratification Measure #2 | Enter the name of the measure on the Pilot Planning Tool Tab
Description of measure | 0 | Description of measure | 0
Population | 0 | Population | 0
Numerator | Enter this descriptive information on the Pilot Planning Tool Tab | Numerator | Enter this descriptive information on the Pilot Planning Tool Tab
Denominator | Enter this descriptive information on the Pilot Planning Tool Tab | Denominator | Enter this descriptive information on the Pilot Planning Tool Tab
Organization Name: | On Schedule of Reporting tab, enter Organization/Plan/Practice Name | Organization Name: | On Schedule of Reporting tab, enter Organization/Plan/Practice Name
Stratification Measure #3 | Enter the name of the measure on the Pilot Planning Tool Tab | Outreach Measure #1 | Enter the name of the measure on the Pilot Planning Tool Tab
Description of measure | 0 | Description of measure | 0
Population | 0 | Population | 0
Numerator | Enter this descriptive information on the Pilot Planning Tool Tab | Numerator | Enter this descriptive information on the Pilot Planning Tool Tab
Denominator | Enter this descriptive information on the Pilot Planning Tool Tab | Denominator | Enter this descriptive information on the Pilot Planning Tool Tab
Organization Name: | On Schedule of Reporting tab, enter Organization/Plan/Practice Name | Organization Name: | On Schedule of Reporting tab, enter Organization/Plan/Practice Name
Outreach Measure #2 | Enter the name of the measure on the Pilot Planning Tool Tab | Outreach Measure #3 | Enter the name of the measure on the Pilot Planning Tool Tab
Description of measure | 0 | Description of measure | 0
Population | 0 | Population | 0
Numerator | Enter this descriptive information on the Pilot Planning Tool Tab | Numerator | Enter this descriptive information on the Pilot Planning Tool Tab
Denominator | Enter this descriptive information on the Pilot Planning Tool Tab | Denominator | Enter this descriptive information on the Pilot Planning Tool Tab
Organization Name: | On Schedule of Reporting tab, enter Organization/Plan/Practice Name | Organization Name: | On Schedule of Reporting tab, enter Organization/Plan/Practice Name
Intervention Measure #1 | Enter the name of the measure on the Pilot Planning Tool Tab | Intervention Measure #2 | Enter the name of the measure on the Pilot Planning Tool Tab
Description of measure | 0 | Description of measure | 0
Population | 0 | Population | 0
Numerator | Enter this descriptive information on the Pilot Planning Tool Tab | Numerator | Enter this descriptive information on the Pilot Planning Tool Tab
Denominator | Enter this descriptive information on the Pilot Planning Tool Tab | Denominator | Enter this descriptive information on the Pilot Planning Tool Tab
Organization Name: | On Schedule of Reporting tab, enter Organization/Plan/Practice Name | Organization Name: | On Schedule of Reporting tab, enter Organization/Plan/Practice Name
Intervention Measure #3 | Enter the name of the measure on the Pilot Planning Tool Tab | Overall Aim Measure #1 | Enter the name of the measure on the Pilot Planning Tool Tab
Description of measure | 0 | Description of measure | Enter this descriptive information on the Pilot Planning Tool Tab
Population | 0 | Population | Enter this descriptive information on the Pilot Planning Tool Tab
Numerator | Enter this descriptive information on the Pilot Planning Tool Tab | Numerator | Enter this descriptive information on the Pilot Planning Tool Tab
Denominator | Enter this descriptive information on the Pilot Planning Tool Tab | Denominator | Enter this descriptive information on the Pilot Planning Tool Tab
Organization Name: | On Schedule of Reporting tab, enter Organization/Plan/Practice Name | Organization Name: | On Schedule of Reporting tab, enter Organization/Plan/Practice Name
Overall Aim Measure #2 | Enter the name of the measure on the Pilot Planning Tool Tab | Overall Aim Measure #3 | Enter the name of the measure on the Pilot Planning Tool Tab
Description of measure | Enter this descriptive information on the Pilot Planning Tool Tab | Description of measure | Enter this descriptive information on the Pilot Planning Tool Tab
Population | Enter this descriptive information on the Pilot Planning Tool Tab | Population | Enter this descriptive information on the Pilot Planning Tool Tab
Numerator | Enter this descriptive information on the Pilot Planning Tool Tab | Numerator | Enter this descriptive information on the Pilot Planning Tool Tab
Denominator | Enter this descriptive information on the Pilot Planning Tool Tab | Denominator | Enter this descriptive information on the Pilot Planning Tool Tab
Organization Name: | On Schedule of Reporting tab, enter Organization/Plan/Practice Name
Overall Aim Measure #4 | Enter the name of the measure on the Pilot Planning Tool Tab
Description of measure | Enter this descriptive information on the Pilot Planning Tool Tab
Population | Enter this descriptive information on the Pilot Planning Tool Tab
Numerator | Enter this descriptive information on the Pilot Planning Tool Tab
Denominator | Enter this descriptive information on the Pilot Planning Tool Tab

## Assessment Scales
Title: | Project Title here
Organization Name: | On Schedule of Reporting tab, enter Organization/Plan/Practice Name
Contact Name: | On Schedule of Reporting tab, enter contact person's name
Contact Phone Number: | On Schedule of Reporting tab, enter phone number (with area code)
Submission Date: | On Schedule of Reporting tab, enter date (DD/MM/YY)
Report Date | Team Assessment Scale | Sustainability Scale | Diffusion Scale
2006-04-15
2006-06-15
2006-08-15
2006-10-15
2006-12-15
Instructions: Please complete this form each quarter as part of your team's quarterly report. Use the the 7-point scale (refer to the comment in cell B7) and determine which score on the scale best describes your team's functional level for the current reporting quarter. Record the corresponding number in the cell corresponding the the reporting quarter. You may wish to ask each team member to assess the team's performance level individually and average those scores for your report. | Team Assessment Definitions: 1=Team Formed Appropriate stakeholders are represented Team leadership identified Team roles established 2=Team Goals Established Team has identified collective goal(s) Team has developed an action plan 3=Team Activity, No Change Team has met regularly within last quarter Team has discussed the change(s) they want to make Team has written an implementation plan with each member’s contribution identified 4=Pilot Effort Underway Team has identified each member’s contributions to the change activity Team has implemented change activity Team has measured change activity 5=Pilot Effort Evaluation Team has met to debrief on the initial pilot change activity and measurements All team members understand the results of the change activity Each team member’s contribution has been documented Team has identified next steps in modifying and improving the change activity 6=Change Has Occurred Team can demonstrate through measurement that change has occurred 7=Change Can Be Sustained Team can demonstrate that a structure or process has been institutionalized so that the change can be sustained over time.
Sustainability Scale Definitions: 1=No Effort No movement toward long-term sustainability 2=Minimal Effort Efforts made to research how to ensure sustainability by obtaining funding and/or changing processes, structures or policies 3=Active Efforts Attempts made to obtain funding and/or change processes, structures or policies to ensure sustainability 4=Limited Sustainability Effort has secured temporary funding and/or changes in process, structure or policies have been temporarily instituted; however, the duration and comprehensiveness of the effort are unclear 5=Successfully Sustained Project has secured long-term funding, and/or has been institutionalized by changes in process, structure, or policies |  | Diffusion Scale Definitions: 1=Spreading the Word Publications describing the best practice. Additional promotion (e.g., website, media, newsletters) describing the best practice 2=Direct Contact Responding to a request for information about the best practice. Presentations describing the best practice (e.g., teleconferences, meetings, list serve) 3=Training Formal training of one or more people in the best practice. Presenting at CHCS Workshops or Technical Assistance 4=Mentoring Mentoring is being provided to a new team which has been formed and has undertaken a replication of the best practice 5=Successful Diffusion One or more teams have been formed and have successfully replicated the best practice.
Note on A7: Instructions: Please complete this form each quarter as part of your team's quarterly report. Use the the 7-point scale (refer to the comment in cell B7) and determine which score on the scale best describes your team's functional level for the current reporting quarter. Record the corresponding number in the cell corresponding the the reporting quarter. You may wish to ask each team member to assess the team's performance level individually and average those scores for your report.
Note on B8: Please Record one number in the cell for your current reporting date. Use this scale: 1 = Team formed 2 = Team goals established 3 = Team activity, no change 4 = Pilot effort underway 5 = Pilot effort evaluation 6 = Change has occurred 7 = Change can be sustained
Note on B7: Team Assessment Definitions: 1=Team Formed Appropriate stakeholders are represented Team leadership identified Team roles established 2=Team Goals Established Team has identified collective goal(s) Team has developed an action plan 3=Team Activity, No Change Team has met regularly within last quarter Team has discussed the change(s) they want to make Team has written an implementation plan with each member’s contribution identified 4=Pilot Effort Underway Team has identified each member’s contributions to the change activity Team has implemented change activity Team has measured change activity 5=Pilot Effort Evaluation Team has met to debrief on the initial pilot change activity and measurements All team members understand the results of the change activity Each team member’s contribution has been documented Team has identified next steps in modifying and improving the change activity 6=Change Has Occurred Team can demonstrate through measurement that change has occurred 7=Change Can Be Sustained Team can demonstrate that a structure or process has been nstitutionalized so that the change can be sustained over time.
Note on B9: Please Record one number in the cell for your current reporting date. Use this scale: 1 = Team formed 2 = Team goals established 3 = Team activity, no change 4 = Pilot effort underway 5 = Pilot effort evaluation 6 = Change has occurred 7 = Change can be sustained
Note on B10: Please Record one number in the cell for your current reporting date. Use this scale: 1 = Team formed 2 = Team goals established 3 = Team activity, no change 4 = Pilot effort underway 5 = Pilot effort evaluation 6 = Change has occurred 7 = Change can be sustained
Note on B11: Please Record one number in the cell for your current reporting date. Use this scale: 1 = Team formed 2 = Team goals established 3 = Team activity, no change 4 = Pilot effort underway 5 = Pilot effort evaluation 6 = Change has occurred 7 = Change can be sustained
Note on B12: Please Record one number in the cell for your current reporting date. Use this scale: 1 = Team formed 2 = Team goals established 3 = Team activity, no change 4 = Pilot effort underway 5 = Pilot effort evaluation 6 = Change has occurred 7 = Change can be sustained
Note on B13: Please Record one number in the cell for your current reporting date. Use this scale: 1 = Team formed 2 = Team goals established 3 = Team activity, no change 4 = Pilot effort underway 5 = Pilot effort evaluation 6 = Change has occurred 7 = Change can be sustained
Note on B14: Please Record one number in the cell for your current reporting date. Use this scale: 1 = Team formed 2 = Team goals established 3 = Team activity, no change 4 = Pilot effort underway 5 = Pilot effort evaluation 6 = Change has occurred 7 = Change can be sustained
Note on B15: Please Record one number in the cell for your current reporting date. Use this scale: 1 = Team formed 2 = Team goals established 3 = Team activity, no change 4 = Pilot effort underway 5 = Pilot effort evaluation 6 = Change has occurred 7 = Change can be sustained
Note on D7: Diffusion Scale Definitions: 1=Spreading the Word Publications describing the best practice. Additional promotion (e.g., website, media, newsletters) describing the best practice 2=Direct Contact Responding to a request for information about the best practice. Presentations describing the best practice (e.g., teleconferences, meetings, list serve) 3=Training Formal training of one or more people in the best practice. Presenting at CHCS Workshops or Technical Assistance 4=Mentoring Mentoring is being provided to a new team which has been formed and has undertaken a replication of the best practice 5=Successful Diffusion One or more teams have been formed and have successfully replicated the best practice.
Note on C7: Sustainability Scale Definitions: 1=No Effort No movement toward long-term sustainability 2=Minimal Effort Efforts made to research how to ensure sustainability by obtaining funding and/or changing processes, structures or policies 3=Active Efforts Attempts made to obtain funding and/or change processes, structures or policies to ensure sustainability 4=Limited Sustainability Effort has secured temporary funding and/or changes in process, structure or policies have been temporarily instituted; however, the duration and comprehensiveness of the effort are unclear 5=Successfully Sustained Project has secured long-term funding, and/or has been institutionalized by changes in process, structure, or policies
Note on D8: Please record one number in the cell for your current reporting date. Use this scale: 1 = Spreading the word 2 = Direct contact 3 = Training 4 = Mentoring 5 = Successful Diffusion
Note on C8: Please record one number in the cell for your current reporting date. Use this scale: 1 = No Effort 2 = Minimal Effort 3 = Active Efforts 4 = Limited Sustainability 5 = Successfully Sustained
Note on D9: Please record one number in the cell for your current reporting date. Use this scale: 1 = Spreading the word 2 = Direct contact 3 = Training 4 = Mentoring 5 = Successful Diffusion
Note on C9: Please record one number in the cell for your current reporting date. Use this scale: 1 = No Effort 2 = Minimal Effort 3 = Active Efforts 4 = Limited Sustainability 5 = Successfully Sustained
Note on D10: Please record one number in the cell for your current reporting date. Use this scale: 1 = Spreading the word 2 = Direct contact 3 = Training 4 = Mentoring 5 = Successful Diffusion
Note on C10: Please record one number in the cell for your current reporting date. Use this scale: 1 = No Effort 2 = Minimal Effort 3 = Active Efforts 4 = Limited Sustainability 5 = Successfully Sustained
Note on D11: Please record one number in the cell for your current reporting date. Use this scale: 1 = Spreading the word 2 = Direct contact 3 = Training 4 = Mentoring 5 = Successful Diffusion
Note on C11: Please record one number in the cell for your current reporting date. Use this scale: 1 = No Effort 2 = Minimal Effort 3 = Active Efforts 4 = Limited Sustainability 5 = Successfully Sustained
Note on D12: Please record one number in the cell for your current reporting date. Use this scale: 1 = Spreading the word 2 = Direct contact 3 = Training 4 = Mentoring 5 = Successful Diffusion
Note on C12: Please record one number in the cell for your current reporting date. Use this scale: 1 = No Effort 2 = Minimal Effort 3 = Active Efforts 4 = Limited Sustainability 5 = Successfully Sustained
Note on D13: Please record one number in the cell for your current reporting date. Use this scale: 1 = Spreading the word 2 = Direct contact 3 = Training 4 = Mentoring 5 = Successful Diffusion
Note on C13: Please record one number in the cell for your current reporting date. Use this scale: 1 = No Effort 2 = Minimal Effort 3 = Active Efforts 4 = Limited Sustainability 5 = Successfully Sustained
Note on D14: Please record one number in the cell for your current reporting date. Use this scale: 1 = Spreading the word 2 = Direct contact 3 = Training 4 = Mentoring 5 = Successful Diffusion
Note on C14: Please record one number in the cell for your current reporting date. Use this scale: 1 = No Effort 2 = Minimal Effort 3 = Active Efforts 4 = Limited Sustainability 5 = Successfully Sustained
Note on D15: Please record one number in the cell for your current reporting date. Use this scale: 1 = Spreading the word 2 = Direct contact 3 = Training 4 = Mentoring 5 = Successful Diffusion
Note on C15: Please record one number in the cell for your current reporting date. Use this scale: 1 = No Effort 2 = Minimal Effort 3 = Active Efforts 4 = Limited Sustainability 5 = Successfully Sustained

## Common Measures Report
COMMON MEASURES | [7 empty] | Yes
Title: |  | Project Title here
Organization Name: |  | On Schedule of Reporting tab, enter Organization/Plan/Practice Name
Contact Name: |  | On Schedule of Reporting tab, enter contact person's name
Contact Phone Number: |  | On Schedule of Reporting tab, enter phone number (with area code)
Submission Date: |  | On Schedule of Reporting tab, enter date (DD/MM/YY)
Common Measure #1 | Enter Name of Measure Here.
Description of measure
Population
Numerator
Denominator
Are the data in the numerator cumlative over time (yes/no)? |  |  |  | Are the data in the denominator cumlative over time (yes/no)?
Notes regarding the data for this measure:
Common measure population |  |  |  | Comparison population (IF APPLICABLE)
Report Date | Numerator (number) | Denominator (number) | Rate or results | Report Date | Numerator (number | Denominator (number) | Rate or results
2006-08-15 |  |  | #DIV/0! | 2006-08-15 |  |  | #DIV/0!
2006-10-15 |  |  | #DIV/0! | 2006-10-15 |  |  | #DIV/0!
2006-12-15 |  |  | #DIV/0! | 2006-12-15 |  |  | #DIV/0!
2007-03-15 |  |  | #DIV/0! | 2007-03-15 |  |  | #DIV/0!
2007-06-15 |  |  | #DIV/0! | 2007-06-15 |  |  | #DIV/0!
2007-09-15 |  |  | #DIV/0! | 2007-09-15 |  |  | #DIV/0!
2007-12-15 |  |  | #DIV/0! | 2007-12-15 |  |  | #DIV/0!
2008-03-15 |  |  | #DIV/0! | 2008-03-15 |  |  | #DIV/0!
2008-06-15 |  |  | #DIV/0! | 2008-06-15 |  |  | #DIV/0!
2008-09-15 |  |  | #DIV/0! | 2008-09-15 |  |  | #DIV/0!
2008-12-15 |  |  | #DIV/0! | 2008-12-15 |  |  | #DIV/0!
2009-03-15 |  |  | #DIV/0! | 2009-03-15
2009-06-15 |  |  | #DIV/0! | 2009-06-15
2009-09-15 |  |  | #DIV/0! | 2009-09-15
2009-12-15 |  |  | #DIV/0! | 2009-12-15
2010-03-15 |  |  | #DIV/0! | 2010-03-15
Common Measure #2 | Enter Name of Measure Here.
Description of measure
Population
Numerator
Denominator
Are the data in the numerator cumlative over time (yes/no)? |  |  |  | Are the data in the denominator cumlative over time (yes/no)?
Notes regarding the data for this measure:
Common measure population |  |  |  | Comparison population (IF APPLICABLE)
Report Date | Numerator (number) | Denominator (number) | Rate or results | Report Date | Numerator (number | Denominator (number) | Rate or results
2006-08-15 |  |  | #DIV/0! | 2006-08-15 |  |  | #DIV/0!
2006-10-15 |  |  | #DIV/0! | 2006-10-15 |  |  | #DIV/0!
2006-12-15 |  |  | #DIV/0! | 2006-12-15 |  |  | #DIV/0!
2007-03-15 |  |  | #DIV/0! | 2007-03-15 |  |  | #DIV/0!
2007-06-15 |  |  | #DIV/0! | 2007-06-15 |  |  | #DIV/0!
2007-09-15 |  |  | #DIV/0! | 2007-09-15 |  |  | #DIV/0!
2007-12-15 |  |  | #DIV/0! | 2007-12-15 |  |  | #DIV/0!
2008-03-15 |  |  | #DIV/0! | 2008-03-15 |  |  | #DIV/0!
2008-06-15 |  |  | #DIV/0! | 2008-06-15 |  |  | #DIV/0!
2008-09-15 |  |  | #DIV/0! | 2008-09-15 |  |  | #DIV/0!
2008-12-15 |  |  | #DIV/0! | 2008-12-15 |  |  | #DIV/0!
2009-03-15 |  |  | #DIV/0! | 2009-03-15 |  |  | #DIV/0!
2009-06-15 |  |  | #DIV/0! | 2009-06-15 |  |  | #DIV/0!
2009-09-15 |  |  | #DIV/0! | 2009-09-15 |  |  | #DIV/0!
2009-12-15 |  |  | #DIV/0! | 2009-12-15 |  |  | #DIV/0!
2010-03-15 |  |  | #DIV/0! | 2010-03-15 |  |  | #DIV/0!
Common Measure #3 | Enter Name of Measure Here.
Description of measure
Population
Numerator
Denominator
Are the data in the numerator cumlative over time (yes/no)? |  |  |  | Are the data in the denominator cumlative over time (yes/no)?
Notes regarding the data for this measure:
Common measure population |  |  |  | Comparison population (IF APPLICABLE)
Report Date | Numerator (number) | Denominator (number) | Rate or results | Report Date | Numerator (number | Denominator (number) | Rate or results
2006-08-15 |  |  | #DIV/0! | 2006-08-15 |  |  | #DIV/0!
2006-10-15 |  |  | #DIV/0! | 2006-10-15 |  |  | #DIV/0!
2006-12-15 |  |  | #DIV/0! | 2006-12-15 |  |  | #DIV/0!
2007-03-15 |  |  | #DIV/0! | 2007-03-15 |  |  | #DIV/0!
2007-06-15 |  |  | #DIV/0! | 2007-06-15 |  |  | #DIV/0!
2007-09-15 |  |  | #DIV/0! | 2007-09-15 |  |  | #DIV/0!
2007-12-15 |  |  | #DIV/0! | 2007-12-15 |  |  | #DIV/0!
2008-03-15 |  |  | #DIV/0! | 2008-03-15 |  |  | #DIV/0!
2008-06-15 |  |  | #DIV/0! | 2008-06-15 |  |  | #DIV/0!
2008-09-15 |  |  | #DIV/0! | 2008-09-15 |  |  | #DIV/0!
2008-12-15 |  |  | #DIV/0! | 2008-12-15 |  |  | #DIV/0!
2009-03-15 |  |  | #DIV/0! | 2009-03-15 |  |  | #DIV/0!
2009-06-15 |  |  | #DIV/0! | 2009-06-15 |  |  | #DIV/0!
2009-09-15 |  |  | #DIV/0! | 2009-09-15 |  |  | #DIV/0!
2009-12-15 |  |  | #DIV/0! | 2009-12-15 |  |  | #DIV/0!
2010-03-15 |  |  | #DIV/0! | 2010-03-15 |  |  | #DIV/0!
Note on A15: First report date is BASELINE data.
Note on E15: Please do not place your data in these cells if the Report Date cells are blank.
Note on A41: First report date is BASELINE data.
Note on E41: Please do not place your data in these cells if the Report Date cells are blank.
Note on A67: First report date is BASELINE data.
Note on E67: Please do not place your data in these cells if the Report Date cells are blank.

## Common Measure Graphs
Organization Name: | On Schedule of Reporting tab, enter Organization/Plan/Practice Name | Organization Name: | On Schedule of Reporting tab, enter Organization/Plan/Practice Name
Common Measure #1 | Enter Name of Measure Here. | Common Measure #1 | Enter Name of Measure Here.
Description of measure | 0 | Description of measure | Comparison population (IF APPLICABLE)
Population | 0 | Population | 0
Numerator | 0 | Numerator | 0
Denominator | 0 | Denominator | 0
Organization Name: | On Schedule of Reporting tab, enter Organization/Plan/Practice Name | Organization Name: | On Schedule of Reporting tab, enter Organization/Plan/Practice Name
Common Measure #2 | Enter Name of Measure Here. | Common Measure #2 | Enter Name of Measure Here.
Description of measure | 0 | Description of measure | Comparison population (IF APPLICABLE)
Population | 0 | Population | 0
Numerator | 0 | Numerator | 0
Denominator | 0 | Denominator | 0
Organization Name: | On Schedule of Reporting tab, enter Organization/Plan/Practice Name | Organization Name: | On Schedule of Reporting tab, enter Organization/Plan/Practice Name
Common Measure #3 | Enter Name of Measure Here. | Common Measure #3 | Enter Name of Measure Here.
Description of measure | 0 | Description of measure | Comparison population (IF APPLICABLE)
Population | 0 | Population | 0
Numerator | 0 | Numerator | 0
Denominator | 0 | Denominator | 0
Organization Name: | On Schedule of Reporting tab, enter Organization/Plan/Practice Name | Organization Name: | On Schedule of Reporting tab, enter Organization/Plan/Practice Name
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
Organization Name: | On Schedule of Reporting tab, enter Organization/Plan/Practice Name | Organization Name: | On Schedule of Reporting tab, enter Organization/Plan/Practice Name
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
Organization Name: | On Schedule of Reporting tab, enter Organization/Plan/Practice Name | Organization Name: | On Schedule of Reporting tab, enter Organization/Plan/Practice Name
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
Organization Name: | On Schedule of Reporting tab, enter Organization/Plan/Practice Name | Organization Name: | On Schedule of Reporting tab, enter Organization/Plan/Practice Name
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
Organization Name: | On Schedule of Reporting tab, enter Organization/Plan/Practice Name
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0