## Sheet1
Innovations in Childhood Obesity (ICO) Project Workplan
State:
Date:
Goals and Objectives |  | Activities | Resources Needed | Anticipated Barriers | Metrics for Objective | Responsible Parties | Timeframe | Other Considerations
GOAL 1 | Increase classroom-based nutrition education in five targeted counties
Objective 1a | Secure commitments from superintendents of schools in the five targeted counties to incorporate obesity-prevention education into classrooms of primary schools. | Meet with school superintendents and school nurses in those counties | Staff time, travel costs | Busy schedules of superintendents and nurses | Number/percentage of school districts in the five counties committing to incorporate obesity-prevention education into the classrooms of their primary schools | Individual name (s), title(s), state department of health | September 2015 - November 2015
|  | Identify and provide grade-specific, obesity-prevention curricula to superintendents and school nurses of targeted school districts and schools |  | Competing educational priorities in limited class time
Objective 1b
GOAL 2